## Revalidation_ Works (Abstract)
Annexure 5: Revalidation Work PIP 2026-27, Odisha
This format is to be used by states for submitting details of approvals accorded in previous years’ RoP, for which revalidation is requested in FY 2026-27 to carry out the approved activities in FY 2026-27. The amount revalidated, will be included in the RoP and the Resource envelope will be reduced by the amount submitted accordingly.
S.No. | Name of the pool and Activity | Year of Approval in RoP | FMR / S.no of RoP (from previous year) | Details of approval | Total amount approved for the activity in the Concerned Year/ Years (Rs. in Lakhs) | Amount Proposed to be revalidated in FY 2026-27 RoP which will be part of RoP of FY 2026-27 | Remarks Current Status / Progress
REVALIDATION WORKS
1 | Blood Bank at DHHs | 2022-24 | HSS.4, Sl No.164 | Total No of Projects: 4 Nos | 704 | 96.96 | Annex-1
Sub Total DHH |  |  |  |  | 704 | 96.96
2 | Construction of new building at SDHs | 2024-26 | HSS.4, Sl No.165 | Total No of Projects: 2 Nos | 6288 | 2358 | Annex-2
Sub Total SDH |  |  |  |  | 6288 | 2358
3 | Construction of new buildings at 27 CHCs | 2022-24 | HSS.4, Sl No.166 | Total No of Projects: 27 Nos | 23013.04 | 4972.182 | Annex-3
4 | Construction of new buildings at 18 CHCs | 2024-26 | HSS.4, Sl No.166 | Total No of Projects: 18 Nos | 17748 | 5529.2562 | Annex-4
Sub Total CHC |  |  |  |  | 40761.04 | 10501.4382
5 | Construction of 24x 7 PHC | 2024-26 | HSS.4, Sl No.167 | Total No of Projects: 45 Nos | 7760.35 | 1917.509 | Annex-5
6 | Construction of Day Care PHC | 2024-26 | HSS.4, Sl No.167 | Total No of Projects: 98 Nos | 6865.12 | 2707.4996
Sub Total PHC |  |  |  |  | 14625.47 | 4625.0086
7 | Constrcution of SCs | 2022-24 | HSS.4, Sl No.168 | Total No of Projects: 290 Nos | 13349.42 | 1867.7971 | Annex-6
8 | Constrcution of SCs | 2024-26 | HSS.4, Sl No.168 | Total No of Projects: 279 Nos | 22495 | 2576.38 | Annex-7
Sub Total SC |  |  |  |  | 35844.42 | 4444.1771
Grand Total Revalidation Works |  |  |  |  | 98222.93 | 22025.5838
Illustration – • If the resource envelope allocated to “X” State in FY 2021–22 was ₹1000 crore and an amount of ₹50 crore was approved in the RoP 2021–22 for construction or procurement activities but the State did not execute or utilise this approved amount during that year due to any reason. • Now, For FY 2026–27 the total resource envelope allocated to “X” State is ₹1500 crore andif the State intends to take up the same construction/procurement activity in FY 2026–27 it must seek fresh approval for that activity. • Thus, after accounting for the proposed ₹50 crore requirement, the State will have ₹1450 crore remaining within the FY 2026–27 resource envelope for seeking fresh approvals for other activities.

## District Abstract 2026-27
District/ Institution Wise Revalidation Works under NHM for PIP 2026-27, Odisha
Type of Institutions |  | DHH |  | SDH |  | Community Health Centers |  |  |  | Primary Health Centers |  |  |  | Sub-Health Centers |  |  |  | Grand Total 2026-27 (Rs. In Lakhs)
FMR
Sl.No. | Name of the District | 2022-24 |  | 2024-26 |  | 2022-24 |  | 2024-26 |  | 2022-24 |  |  |  | 2022-24 |  | 2024-26
|  | Construction of Blood Bank |  | Building for Existing SDHs |  | New Building for Existing CHC |  |  |  | 24x7 |  | Day Care |  | Construction of SHCs
|  | No. of Works | Budget | No. of Works | Budget | No. of Works | Budget | No. of Works | Budget | No. of Works | Budget | No. of Works | Budget | No. of Works | Budget | No. of Works | Budget
1 | Anugola | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 19.4 | 6 | 54 | 7 | 70 | 143.4
2 | Baleshwar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 23.43 | 16 | 110.53 | 133.96
3 | Baragada | 0 | 0 | 0 | 0 | 3 | 476.532 | 1 | 244.182 | 4 | 173.8 | 5 | 291.62 | 13 | 117 | 0 | 0 | 1303.134
4 | Bhadrak | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 245.4 | 0 | 0 | 0 | 0 | 1 | 4.6 | 0 | 0 | 250
5 | Balangir | 1 | 35.2 | 0 | 0 | 6 | 847.441 | 1 | 246.339 | 4 | 175.23 | 13 | 252.2 | 8 | 31.65 | 19 | 97.85 | 1685.91
6 | Boudh | 0 | 0 | 0 | 0 | 2 | 562.445 | 0 | 0 | 3 | 135.45 | 3 | 83.571 | 0 | 0 | 5 | 50 | 831.466
7 | Kataka | 0 | 0 | 0 | 0 | 1 | 487.151 | 1 | 411 | 3 | 192.15 | 8 | 103.2 | 6 | 53.92 | 6 | 60 | 1307.421
8 | Debagada | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 99.92 | 2 | 42.24 | 0 | 0 | 9 | 90 | 232.16
9 | Dhenkanal | 0 | 0 | 0 | 0 | 2 | 249.792 | 0 | 0 | 2 | 86.2 | 8 | 421.93 | 29 | 257.3371 | 0 | 0 | 1015.259
10 | Gajapati | 0 | 0 | 0 | 0 | 1 | 117.645 | 1 | 411 | 4 | 174.52 | 3 | 117.38 | 15 | 135 | 0 | 0 | 955.545
11 | Ganjam | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 411 | 0 | 0 | 1 | 28.491 | 16 | 223.84 | 1 | 10 | 673.331
12 | Jagatsinghpur | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 488.184 | 0 | 0 | 4 | 130.2366 | 0 | 0 | 18 | 180 | 798.4206
13 | Jajpur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Jharsuguda | 0 | 0 | 0 | 0 | 2 | 830.242 | 0 | 0 | 0 | 0 | 1 | 9.891 | 0 | 0 | 1 | 10 | 850.133
15 | Kalahandi | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 488.262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 488.262
16 | Kandhamal | 1 | 35.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 200.82 | 0 | 0 | 0 | 0 | 236.17
17 | Kendrapada | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 39.18 | 6 | 89.412 | 6 | 7.9 | 0 | 0 | 136.492
18 | Kendujhar | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 243.285 | 0 | 0 | 0 | 0 | 1 | 4 | 20 | 200 | 447.285
19 | Khordha | 1 | 10 | 0 | 0 | 3 | 406.08 | 0 | 0 | 1 | 86.02 | 1 | 54 | 10 | 39.34 | 17 | 170 | 765.44
20 | Koraput | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 411 | 0 | 0 | 0 | 0 | 34 | 306 | 5 | 50 | 767
21 | Malkanagiri | 0 | 0 | 0 | 0 | 1 | 153.013 | 1 | 244.2 | 3 | 115.028 | 4 | 154 | 0 | 0 | 19 | 190 | 856.241
22 | Mayurbhanj | 0 | 0 | 1 | 1048 | 3 | 205.149 | 1 | 206.3712 | 3 | 79.41 | 3 | 27 | 91 | 369.98 | 8 | 80 | 2015.9102
23 | Nabarangpur | 0 | 0 | 0 | 0 | 1 | 153.419 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 9 | 19 | 190 | 352.419
24 | Nayagada | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 77.061 | 9 | 229.21 | 8 | 54.4 | 16 | 88 | 448.671
25 | Nuapada | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 43.92 | 1 | 0.73 | 0 | 0 | 0 | 0 | 44.65
26 | Puri | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 246.033 | 0 | 0 | 6 | 189.845 | 23 | 27.8 | 12 | 120 | 583.678
27 | Rayagada | 0 | 0 | 0 | 0 | 1 | 330.799 | 0 | 0 | 0 | 0 | 1 | 41.083 | 16 | 144 | 19 | 190 | 705.882
28 | Sambalpur | 0 | 0 | 1 | 1310 | 0 | 0 | 1 | 411 | 3 | 131.11 | 3 | 102.9 | 1 | 4.6 | 25 | 250 | 2209.61
29 | Sonpur | 0 | 0 | 0 | 0 | 1 | 152.474 | 1 | 411 | 7 | 308.51 | 7 | 118.34 | 0 | 0 | 18 | 180 | 1170.324
30 | Sundaragada | 1 | 16.41 | 0 | 0 | 0 | 0 | 1 | 411 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 190 | 617.41
31 | Capital Hospital, BBSR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | RGH, Rourkella | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | SCB MCH, Kataka | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | MKCG, MCH Brahmapur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | VIMSAR, MCH Burla | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | SVPPGIP, Kataka | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | Bhubaneswar CHS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | Kataka CHS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | Sambalpur CHS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | Brahmapur CHS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | Rourkella CHS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | FM MCH, Baleshwar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | BB MCH, Balangir | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | SLN MCH, Koraput | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | PRM MCH, Mayurbhanj | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | SJ MCH, Puri | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | AHRCC, Kataka | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | MHI, Kataka | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | DD, MCH, Kendujhar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | GMCH, Sundaragada | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | SCB Dental, Kataka | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | MCH Kalahandi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | MCH Talcher, Anugola | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | MCH Jajpur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | MCH Kandhamal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | PGIMER, Capital Hospital, Bhubaneswar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | AIIMS, Bhubaneswar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | State | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 4 | 96.96 | 2 | 2358 | 27 | 4972.182 | 18 | 5529.2562 | 45 | 1917.509 | 98 | 2707.4996 | 290 | 1867.7971 | 279 | 2576.38 | 22025.5838
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
0

## Abstract Revalidation Works
Abstract Revalidation Works, Odisha
Sl. No. | District | 2022-24 | [5 empty] | 2024-26
|  | DHH | CHC | PHC (24x7) | Day Care | SC | Total | SDH | CHC | SC | Total
|  | Fund Proposed | Fund Proposed | Fund Proposed | Fund Proposed | Fund Proposed |  | Fund Proposed | Fund Proposed | Fund Proposed
1 | Angul |  |  |  | 1 | 6 | 7 |  |  | 7 | 7
2 | Balasore |  |  |  |  | 5 | 5 |  |  | 16 | 16
3 | Baragada |  | 3 | 4 | 5 | 13 | 25 |  | 1 | 0 | 1
4 | Bhadrak |  |  |  |  | 1 | 1 |  | 1 | 0 | 1
5 | Balangirr | 1 | 6 | 4 | 13 | 8 | 32 |  | 1 | 19 | 20
6 | Boudh |  | 2 | 3 | 3 | 0 | 8 |  |  | 5 | 5
7 | Kataka |  | 1 | 3 | 8 | 6 | 18 |  | 1 | 6 | 7
8 | Debagada |  |  | 1 | 2 | 0 | 3 |  |  | 9 | 9
9 | Dhenkanal |  | 2 | 2 | 8 | 29 | 41 |  | 1 | 0 | 1
10 | Gajapati |  | 1 | 4 | 3 | 15 | 23 |  | 1 | 0 | 1
11 | Ganjam |  |  |  | 1 | 16 | 17 |  |  | 1 | 1
12 | Jagatsinghpur |  |  |  | 4 | 0 | 4 |  | 2 | 18 | 20
13 | Jajpur |  |  |  |  | 0 | 0 |  |  | 0 | 0
14 | Jharsuguda |  | 2 |  | 1 | 0 | 3 |  |  | 1 | 1
15 | Kalahandi |  |  |  | 0 | 0 | 0 |  | 2 | 0 | 2
16 | Kandhamal | 1 |  |  | 8 | 0 | 9 |  | 0 | 0 | 0
17 | Kendrapada |  |  | 4 | 6 | 6 | 16 |  |  | 0 | 0
18 | Keonjhar |  |  |  |  | 0 | 0 |  | 1 | 20 | 21
19 | Khordha | 1 | 3 | 1 | 1 | 10 | 16 |  |  | 17 | 17
20 | Koraput |  |  |  |  | 34 | 34 |  | 1 | 5 | 6
21 | Malkanagiri |  | 1 | 3 | 4 |  | 8 |  | 1 | 19 | 20
22 | Mayurbhanj |  | 3 | 3 | 3 | 92 | 101 | 1 | 1 | 8 | 10
23 | Nabarangpur |  | 1 |  |  | 1 | 2 |  |  | 19 | 19
24 | Nayagada |  |  | 2 | 9 | 8 | 19 |  |  | 16 | 16
25 | Nuapada |  |  | 1 | 1 | 0 | 2 |  |  | 0 | 0
26 | Puri |  |  |  | 6 | 23 | 29 |  | 1 | 12 | 13
27 | Rayagada |  | 1 |  | 1 | 16 | 18 |  |  | 19 | 19
28 | Sambalpur |  |  | 3 | 3 | 1 | 7 | 1 | 1 | 25 | 27
29 | Sonpur |  | 1 | 7 | 7 | 0 | 15 |  | 1 | 18 | 19
30 | Sundaragada | 1 |  |  |  | 0 | 1 |  | 1 | 19 | 20
Total |  | 4 | 27 | 45 | 98 | 290 | 464 | 2 | 18 | 279 | 299

## Annex-1 DHH 22-24
Status of Civil Construction under NHM PIP Works approved during 2022-24, Odisha
Sl. No. | Name of the District | NameoftheFacility | Type of Facility | Name of the work | Year of Sanction of works | Total Project Cost approved (in Rs. Lakhs) | Revised cost in 2024-26 (In lakh) | Re- Revised cost in 2026-27 (In lakh) | Amount Sanctioned till 2025-26 (Rs in Lakh) | Approved in Supplementary PIP 25-26 | Total Approval | Expenditure till August 2025 (Rs in Lakhs) | Physical Status of the work till August 2025 | Status of Works |  | Estimated year / month of completion of work | Remarks | Fund Approved in 2026-27 (Rs. In Lakhs)
In progress/ Not Started
1 | Completed
1 | Balangir | OBCDHH,Balangir | DHH | Construction of New Blood Bank | 2022-24 | 176 | 176 |  | 140.8 |  | 140.8 | 176 | Completed and handedover | Completed |  | 17.04.2024 |  | 35.2
2 | Kandhamal | OBC DHH, Phulbani | DHH | Construction of New Blood Bank | 2022-24 | 176 | 176.76 |  | 141.41 |  | 141.41 | 127.88 | Finishing Stage | Finishing Stage |  | 31.10.2025 |  | 35.35
3 | Khordha | OBC DHH, Khordha | DHH | Construction of New Blood Bank | 2022-24 | 176 | 186 |  | 176 |  | 176 | 139.56 | Completed & handed over |  |  |  |  | 10
4 | Sundaragada | OBC DHH, Sundergarh | DHH | Construction of New Blood Bank | 2022-24 | 176 | 192.41 |  | 176 |  | 176 | 118.487 | Finishing & Ply partition work in progress | Finishing Stage |  | 30.10.2025 |  | 16.41
| Sub Total |  |  |  |  | 704 | 731.17 | 0 | 634.21 | 0 | 634.21 | 561.927 |  | 0 | 0 | 0 | 0 | 96.96

## Annex-2-SDH 24-26
Fund Requirement for Spillover /Ongoing Works approved under NHM 2024-26, Odisha
Sl. No. | Name of the District | Name of the Block | Name of the Facility | Type of Facility | Name of the work | Year of Sanction of works | Total Project Cost approved in 2024-26 (in Rs. Lakhs) | Project Cost(In lakh) | Amount Sanctioned till 2025-26 (Rs in Lakh) | Expenditure till July 2025 (Rs in Lakhs) | Physical Status of the work till July' 2025 | Status of Works | Fund Approved in 2026-27 (Rs. In Lakhs) | Remarks
In progress/ Not Started
1 | Mayurbhanj | Rairangpur | Rairangpur | SDH | New Building for Existing SDHs | 2024-26 | 5240 | 5240 | 3144 |  |  | Plinth Level | 1048 | Fund Proposed: 50% of the balance requirement
2 | Sambalpur | Kuchinda | Kuchinda | SDH | New Building for Existing SDHs | 2024-26 | 5240 | 5240 | 3144 |  |  | The work will be constructed at new site in the existing SDH campus | 1310 | As the work not started hence reproposed in 2026-27
| Sub Total | [5 empty] | 10480 | 10480 | 6288 | 0 | 0 | 0 | 2358 | 0

## Annex-3- CHC 22-24
Status of Civil Construction under NHM PIP Works approved during 2022-24, Odisha
Sl. No. | Name of the District | Name of the Facility | Type of Facility | Name of the work | Year of Sanction of works | Total Project Cost approved (in Rs. Lakhs) | Revised cost in 2024-26 (In lakh) | Revised cost in 2026-27 (In lakh) | Amount Sanctioned till 2025-26 (Rs in Lakh) | Approved in Supplementary PIP 25-26 | Total Approval | Expenditure till August 2025 (Rs in Lakhs) | Physical Status of the work till August 2025 | Status of Works | Estimated year / month of completion of work | Remarks | Fund Approved in 2026-27 (Rs. In Lakhs) | Remarks
In progress/ Not Started
1 | Baragada | Agalpur CHC | CHC | New Building for Existing CHC | 2022-24 | 994 | 1032.13 | 1072.73 | 825.7 | 0 | 825.7 | 584.17 | In finishing stage | Finishing Stage | 31.10.2025 |  | 172.921 | Placed at Estimation Folder At sl no. 5 CHC
2 | Baragada | Bhukta CHC | CHC | New Building for Existing CHC | 2022-24 | 994 | 1073.5 | 1076.19 | 858.8 | 0 | 858.8 | 590.42 | In finishing stage | Finishing Stage | 31.10.2025 |  | 152.173 | Placed at Estimation Folder At sl no. 4 CHC
3 | Baragada | Gaisilet CHC | CHC | New Building for Existing CHC | 2022-24 | 994 | 1068.37 | 1071.04 | 854.7 | 0 | 854.7 | 587.6 | In finishing stage | Finishing Stage | 31.10.2025 |  | 151.438 | Placed at Estimation Folder At sl no. 6 CHC
4 | Balangir | Agalpur CHC. | CHC | New Building for Existing CHC | 2022-24 | 994 | 1088.95 |  | 871.16 | 0 | 871.16 | 904 | Civil work to be completed,Fire fighting work inprogress | Finishing Stage | 30.10.2025 |  | 152.453
5 | Balangir | Belpara | CHC | Construction of 30 bedded MCH wing | 2022-24 | 975 | 1088.29 |  | 964.33 | 0 | 964.33 | 882 | Completed in all respect | Completed | 25.06.2024 |  | 86.772
6 | Balangir | Loisingha CHC | CHC | New Building for Existing CHC | 2022-24 | 994 | 1083.66 |  | 866.93 | 0 | 866.93 | 903 | Civil work to be completed,Fire fighting work inprogress | Finishing Stage | 15..09.2025 |  | 151.711
7 | Balangir | Muribahal CHC | CHC | New Building for Existing CHC | 2022-24 | 994 | 1086.3 |  | 869.04 | 0 | 869.04 | 825 | Plastering work inprogress | in Progress | 30.12.2025 |  | 152.082
8 | Balangir | Saintala CHC | CHC | New Building for Existing CHC | 2022-24 | 994 | 1087.37 |  | 869.9 | 0 | 869.9 | 840 | Tiling work inprogress | in Progress | 30.11.2025 |  | 152.229
9 | Balangir | Sindheikela CHC | CHC | New Building for Existing CHC | 2022-24 | 994 | 1087.09 |  | 869.67 | 0 | 869.67 | 904 | Completed in all respect | Completed | 25.06.2024 |  | 152.194
10 | Boudh | Purunakatak | CHC | New Building for Existing CHC | 2022-24 | 994 | 1081.75 |  | 865.4 | 0 | 865.4 | 713.89 | Completed | Completed | 03.02.24 |  | 151.445
11 | Boudh | Adenigarh | CHC | New Building for Existing CHC | 2022-24 (Sup) | 994 | 1644 |  | 994 |  | 994 |  | Work Not Started | Reproposed |  |  | 411
12 | Kataka | Subarnapur CHC | CHC | New Building for Existing CHC | 2022-24 | 994 | 1092.95 | 1192.93 | 497 | 0 | 497 | 600 | Completed but EI & PH works is in progress | Finishing Stage | 30.10.2025 |  | 487.151 | Placed at Estimation Folder Annex at Sl No. 14_CHC
13 | Dhenkanal | AnlabarenI CHC | CHC | New Building for Existing CHC | 2022-24 | 994 | 1040.79 |  | 832.63 | 0 | 832.63 | 300 | Plastering work inprogress | Finishing Stage | 31.12.2025 |  | 104.08
14 | Dhenkanal | OdapadaCHC | CHC | New Building for Existing CHC | 2022-24 | 994 | 1040.79 |  | 832.63 | 0 | 832.63 | 107 | Finishing work in Progress | Finishing Stage | 28.02.2026 |  | 145.712
15 | Gajapati | Gumma CHC | CHC | New Building for Existing CHC | 2022-24 | 994 | 1063.8 | 1086.33 | 851.04 | 0 | 851.04 | 512 | Second floor plastering work in progress | Finishing Stage | 6.06.2026 |  | 117.645 | Placed at Estimation Folder Annex at Sl No. 17_CHC
16 | Jharsuguda | Kolabira CHC | CHC | New Building for Existing CHC | 2022-24 | 994 | 1087.07 |  | 497 | 0 | 497 | 366.19 | Completed |  | 12.11.2025 |  | 413.049 | Placed at Estimation Folder
17 | Jharsuguda | Mundrajore CHC | CHC | New Building for Existing CHC | 2022-24 | 994 |  | 1092.99 | 497 | 0 | 497 | 273.81 | Finishing work in progress (Colouring work ) | in progress | 12.11.2025 |  | 417.193 | Placed at Estimation Folder Annex at Sl No. 20_CHC
18 | Khordha | Bankoi CHC | CHC | New Building for Existing CHC | 2022-24 | 994 | 1055 |  | 844 | 0 | 844 | 388.2 | Finishing work in progress | in progress | 30.11.2025 |  | 147.7 | Placed at Estimation Folder
19 | Khordha | Gambharimunda CHC | CHC | New Building for Existing CHC | 2022-24 | 994 | 1067 |  | 853.6 | 0 | 853.6 | 449.07 | Plastering work in progress | in progress | 31.12.2025 |  | 149.38 | Placed at Estimation Folder
20 | Khordha | Haladia CHC | CHC | New Building for Existing CHC | 2022-24 | 994 | 1090 |  | 872 | 0 | 872 | 185.24 | Ground floor Roof level | in progress | 03.05.2026 |  | 109 | Placed at Estimation Folder
21 | Malkanagiri | Kudumulugumma CHC | CHC | New Building for Existing CHC | 2022-24 | 994 | 1092.96 |  | 874.37 | 0 | 874.37 | 556.43 | finishing work in progress | Finishing Stage | 30.11.2025 |  | 153.013 | Placed at Estimation Folder
22 | Mayurbhanj | Badampahara CHC | CHC | New Building for Existing CHC | 2022-24 | 994 | 1054.77 | 1187.98 | 874.4 | 180.37 | 1054.77 | 637.57 | Finishing work in progress | Finishing Stage | 30.10.2025 |  | 93.247 | Placed at Estimation Folder annex at Sl No. 36_CHC
23 | Mayurbhanj | K.C. Pur CHC | CHC | New Building for Existing CHC | 2022-24 | 994 | 1093.4 | 1181.79 | 874.72 | 218.68 | 1093.4 | 660 | Finishing work in progress | Finishing Stage | 30.10.2025 |  | 61.873 | Placed at Estimation Folder annex at Sl No. 35_CHC
24 | Mayurbhanj | Thakurmunda CHC | CHC | New Building for Existing CHC | 2022-24 | 994 | 1093.4 | 1164.87 | 874.72 | 218.68 | 1093.4 | 726.15 | Finishing work in progress | Finishing Stage | 30.10.2025 |  | 50.029 | Placed at Estimation Folder annex at Sl No. 37_CHC
25 | Nabarangpur | Pujariguda | CHC | New Building for Existing CHC | 2022-24 | 994 | 1095.86 |  | 876.69 | 0 | 876.69 | 401.333 | completed |  |  |  | 153.419 | Placed at Estimation Folder
26 | Rayagada | CHC Muniguda | CHC | New Building for Existing CHC | 2022-24 | 994 | 1078.25 | 1335.17 | 862.6 | 0 | 862.6 | 680 | fire fighting work in pending | Finishing Stage | 30.11.2025 |  | 330.799 | Placed at Estimation Folder annex at Sl No. 44_CHC
27 | Sonpur | Tarava CHC | CHC | New Building for Existing CHC | 2022-24 | 994 | 1089.1 |  | 871.28 | 0 | 871.28 | 544.55 | Finishing work in progress | in progress | 30.11.2025 |  | 152.474
| Total |  |  |  |  | 26819 | 28556.55 | 11462.02 | 22395.31 | 617.73 | 23013.04 | 15121.623 | 0 | 0 | 0 | 0 | 4972.182

## Annex-4- CHC 24-26
Fund Requirement for Spillover /Ongoing Works approved under NHM 2024-26, Odisha
Sl. No. | Name of the District | Name of the Block | Name of the Facility | Type of Facility | Name of the work | Year of Sanction of works | Total Project Cost approved in 2024-26 (in Rs. Lakhs) | Revised cost in 2026-27(In lakh) if, any | Amount Sanctioned till 2025-26 (Rs in Lakh) | Expenditure till July 2025 (Rs in Lakhs) | Physical Status of the work till July' 2025 | Status of Works | Estimated year / month of completion of work | Fund Approved in 2026-27 (Rs. In Lakhs) | Remarks
In progress/ Not Started
1 | Baragada | Paikamal | Paikmal | CHC | New Building for Existing CHCs | 2024-26 | 1644 | 1799.94 | 986 |  |  | foundation stage |  | 244.182 | Revised Estimate placed at Annex-1 in Estimation Folder
2 | Bhadrak | Tihidi | Tihidi | CHC | New Building for Existing CHCs | 2024-26 | 1644 | 1804 | 986 |  |  | Revised estimate under preparation |  | 245.4 | Revised Estimate placed at Annex-2 Estimation Folder
3 | Balangir | Balangir | Chudapali | CHC | New Building for Existing CHCs | 2024-26 | 1644 | 1807.13 | 986 |  |  | Aggrement to be drawn |  | 246.339 | Revised Estimate placed at Annex-3 Estimation Folder
4 | Kataka | Narsinghpur | Narsinghpur | CHC | New Building for Existing CHCs | 2024-26 | 1644 |  | 986 |  |  | land Available, agency not finalised |  | 411 | As the work not started hence reproposed in 2026-27
5 | Gajapati | Kashinagar | Kashinagar | CHC | New Building for Existing CHCs | 2024-26 | 1644 |  | 986 |  |  |  |  | 411 | As the work not started hence reproposed in 2026-27
6 | Ganjam | Purushottampur | Bhatakumarada | CHC | New Building for Existing CHCs | 2024-26 | 1644 |  | 986 |  |  |  |  | 411 | As the work not started hence reproposed in 2026-27
7 | Jagatsinghpur | Biridi | Biridi | CHC | New Building for Existing CHCs | 2024-26 | 1644 | 1799.3 | 986 |  |  | Column casted up to roof level |  | 243.99 | Revised Estimate placed at Annex-7 Estimation Folder
8 | Jagatsinghpur | Erasama | Ersama | CHC | New Building for Existing CHCs | 2024-26 | 1644 | 1799.98 | 986 |  |  | Dismantalling work in progress |  | 244.194 | Revised Estimate placed at Annex-8 Estimation Folder
9 | Kalahandi | Kalampur | Kalampur | CHC | New Building for Existing CHCs | 2024-26 | 1644 | 1799.56 | 986 |  |  | Ground floor roof level |  | 244.068 | Revised Estimate placed at Annex-9 Estimation Folder
10 | Kalahandi | Madanpur Rampur | Madanpur Rampur | CHC | New Building for Existing CHCs | 2024-26 | 1644 | 1799.98 | 986 |  |  | Second floor eroof level |  | 244.194 | Revised Estimate placed at Annex-10 Estimation Folder
| Kandhamal | Raikia | Raikia | CHC | New Building for Existing CHCs | 2024-26 | 1644 |  |  |  |  | Land not finalised |  |  | Land Not Available, Hence dropped
11 | Kendujhar | Jhumpura | Jhumpura | CHC | New Building for Existing CHCs | 2024-26 | 1644 | 1796.95 | 986 |  |  | SF Roof level |  | 243.285 | Revised Estimate placed at Annex-12 Estimation Folder
12 | Koraput | Similiguda | Sunabeda | CHC | New Building for Existing CHCs | 2024-26 | 1644 |  | 986 |  |  | Site finalised, agency not finalised |  | 411 | As the work not started hence reproposed in 2026-27
13 | Malkanagiri | Malkangiri | Pandripani | CHC | New Building for Existing CHCs | 2024-26 | 1644 | 1800 | 986 |  |  | Plinth Level |  | 244.2 | Revised Estimate placed at Annex-14 Estimation Folder
14 | Mayurbhanj | Kaptipada | Kaptipada | CHC | New Building for Existing CHCs | 2024-26 | 1644 | 1673.904 | 986 |  |  | Foundation work in progress |  | 206.3712 | Revised Estimate placed at Annex-15 Estimation Folder
15 | Puri | Pipili | Managalpur | CHC | New Building for Existing CHCs | 2024-26 | 1644 | 1806.11 | 986 |  |  | Work Order issued |  | 246.033 | Revised Estimate placed at Annex-16 Estimation Folder
16 | Sambalpur | Bamra | Garposh | CHC | New Building for Existing CHCs | 2024-26 | 1644 |  | 986 |  |  |  |  | 411 | As the work not started hence reproposed in 2026-27
17 | Sonpur | Binka | Binka | CHC | New Building for Existing CHCs | 2024-26 | 1644 |  | 986 |  |  | Letter issued to S.E PWD for submission of Estimate of CHC Building |  | 411 | As the work not started hence reproposed in 2026-27
18 | Sundaragada | Bisra | Bisra | CHC | New Building for Existing CHCs | 2024-26 | 1644 |  | 986 |  |  |  |  | 411 | As the work not started hence reproposed in 2026-27
| Sub Total | [5 empty] | 31236 | 19686.854 | 17748 | 0 | 0 | 0 | 0 | 5529.2562
8840.854

## Annex-5-PHC 2022-24
Status of Civil Construction under NHM PIP Works approved during 2022-24
Sl. No. | Name of the District | NameoftheFacility | Type of Facility | Name of the work | Year of Sanction of works | Total Project Cost approved (in Rs. Lakhs) | Revised cost in 2024-26 (In lakh) | Revised cost in 2026-27 (In lakh) | Amount Sanctioned till 2025-26 (Rs in Lakh) | Approved in Supplementary PIP 25-26 | Total Approval | Expenditure till August 2025 (Rs in Lakhs) | Physical Status of the work till August 2025 | Estimated year / month of completion of work |  | Fund Approved in 2026-27 (Rs. In Lakhs) | Remarks
1 | Baragada | Kharamunda | PHC | PHC 24x7 Building | 2022-24 | 200 | 217.13 |  | 173.7 | 0 | 173.7 | 32.5 | Completed |  |  | 43.43
2 | Baragada | Talpadar | PHC | PHC 24x7 Building | 2022-24 | 200 | 217.23 |  | 173.78 | 0 | 173.78 | 32.5 | Completed |  |  | 43.45
3 | Baragada | Jharabandha | PHC | PHC 24x7 Building | 2022-24 | 200 | 217.89 |  | 174.31 | 0 | 174.31 | 32.5 | Completed |  |  | 43.58
4 | Baragada | Jamsat | PHC | PHC 24x7 Building | 2022-24 | 200 | 216.69 |  | 173.35 | 0 | 173.35 | 32.5 | Completed |  |  | 43.34
5 | Balangir | Bangomunda | PHC | PHC 24x7 Building | 2022-24 | 200 | 219.96 |  | 175.97 | 0 | 175.97 | 189.19 | Completed and handedover | 25.03.2024 |  | 43.99
6 | Balangir | Kusanga | PHC | PHC 24x7 Building | 2022-24 | 200 | 217.62 |  | 174.1 | 0 | 174.1 | 213.49 | Completed and handedover | 25.03.2024 |  | 43.52
7 | Balangir | Mahimunda | PHC | PHC 24x7 Building | 2022-24 | 200 | 219.89 |  | 175.91 | 0 | 175.91 | 217.94 | Completed and handedover | 25.03.2024 |  | 43.98
8 | Balangir | Tikrapada | PHC | PHC 24x7 Building | 2022-24 | 200 | 218.68 |  | 174.94 | 0 | 174.94 | 215.86 | Completed and handedover | 25.03.2024 |  | 43.74
9 | Boudh | Baghiapada | PHC | PHC 24x7 Building | 2022-24 | 200 | 212.57 |  | 171.71 | 0 | 171.71 | 142.79 | Completed & Handed over | 21.11.23 |  | 40.86
10 | Boudh | Sagada | PHC | PHC 24x7 Building | 2022-24 | 200 |  | 214.64 | 170.05 | 0 | 170.05 | 139.62 | Completed & Handed over | 21.11.23 |  | 44.59 | Placed at Estimation Folder Annex at Sl No. 16 _PHC
11 | Boudh | Talagaon | PHC | PHC 24x7 Building | 2022-24 | 200 |  |  | 120 | 0 | 120 |  | OPHWC is framing estimate with structural design | 21.11.23 | Reproposed | 50
12 | Kataka | Tulasipur | PHC | PHC 24x7 Building | 2022-24 | 200 | 218.98 |  | 175.18 | 0 | 175.18 | 206.67 | Completed & Handed over |  |  | 43.8
13 | Kataka | Govindpur | PHC | PHC 24x7 Building | 2022-24 | 200 | 218.35 |  | 120 | 0 | 120 | 100.97 | Completed & Handed over |  |  | 98.35
14 | Kataka | Bhiruda | PHC | PHC 24x7 Building | 2022-24 | 200 |  |  | 120 | 0 | 120 | 100.97 | Site Finalized, Reporoposed |  | Reproposed | 50
15 | Debagada | PalasamaOH | PHC | PHC 24x7 Building | 2022-24 | 200 | 219.92 |  | 120 | 0 | 120 | 219 | Completed | 2025-08-29 |  | 99.92
16 | Dhenkanal | Marthapur | PHC | PHC 24x7 Building | 2022-24 | 200 | 215.52 |  | 172.42 | 0 | 172.42 | 160 | completed |  |  | 43.1
17 | Dhenkanal | Baladiabandha | PHC | PHC 24x7 Building | 2022-24 | 200 | 215.52 |  | 172.42 | 0 | 172.42 | 80 | Finishing work in progress | 31.10.2025 |  | 43.1
18 | Gajapati | Jeerango | PHC | PHC 24x7 Building | 2022-24 | 200 | 218.17 |  | 174.54 | 0 | 174.54 | 171.15 | Completed |  |  | 43.63
19 | Gajapati | Koinpur | PHC | PHC 24x7 Building | 2022-24 | 200 | 218.17 |  | 174.54 | 0 | 174.54 | 167.57 | EI PH in progress | 30.10.2025 |  | 43.63
20 | Gajapati | Nuagada | PHC | PHC 24x7 Building | 2022-24 | 200 | 218.17 |  | 174.54 | 0 | 174.54 | 149.49 | External EI pending |  |  | 43.63
21 | Gajapati | Ramagiri | PHC | PHC 24x7 Building | 2022-24 | 200 | 218.17 |  | 174.54 | 0 | 174.54 | 195.5 | External EI pending |  |  | 43.63
22 | Kendrapada | Mundala-Harianka | PHC | PHC 24x7 Building | 2022-24 | 200 | 238.8 |  | 120 | 113 | 233 | 100 | 1st floor Roof Cast | 15.12.2025 |  | 5.8
23 | Kendrapada | Sanajaria | PHC | PHC 24x7 Building | 2022-24 | 200 | 240.91 |  | 120 | 113 | 233 | 72.27 | Roof Level | 15.12.2025 |  | 7.91
24 | Kendrapada | Rankalaraghunathpur | PHC | PHC 24x7 Building | 2022-24 | 200 | 245.08 |  | 120 | 113 | 233 | 73.74 | Upto Plinth Level | 15.12.2025 |  | 12.08
25 | Kendrapada | Gupti | PHC | PHC 24x7 Building | 2022-24 | 200 | 246.39 |  | 120 | 113 | 233 | 73.92 | Plinth Level | 15.12.2025 |  | 13.39
26 | Khordha | Malipada | PHC | PHC 24x7 Building | 2022-24 | 200 |  | 206.02 | 120 | 0 | 120 | 61.8 | Finishing work in progress | 30.12.2025 |  | 86.02 | Placed at Estimation Folder Annex at Sl No. 52_PHC
27 | Malkanagiri | Bhejangiwada | PHC | PHC 24x7 Building | 2022-24 | 200 | 215.45 |  | 172.36 | 0 | 172.36 | 60 | finishing work in progress | 2025-11-30 |  | 43.09
28 | Malkanagiri | Pedakonda | PHC | PHC 24x7 Building | 2022-24 | 200 | 215.9 |  | 172.72 | 0 | 172.72 | 60 | finishing work in progress | 2025-11-30 |  | 43.18
29 | Malkanagiri | Motu | PHC | PHC 24x7 Building | 2022-24 | 200 | 215.86 |  | 120 | 0 | 120 | 0 | Foundation level | 2026-06-30 |  | 28.758
30 | Mayurbhanj | KuamaraOH | PHC | PHC 24x7 Building | 2022-24 | 200 |  | 220 | 120 | 80.82 | 200.82 | 69.6 | Completed |  |  | 19.18 | Placed at Estimation Folder Annex at Sl No. 61_PHC
31 | Mayurbhanj | Manida | PHC | PHC 24x7 Building | 2022-24 | 200 |  | 220 | 120 | 80 | 200 | 69.6 | Finishing work in progress | 30.10.2025 |  | 20 | Placed at Estimation Folder Annex at Sl No. 63_PHC
32 | Mayurbhanj | Ghagarbeda | PHC | PHC 24x7 Building | 2022-24 | 200 |  | 254.1 | 120 | 0 | 120 |  | Work to be started(Recently Land handed over to HSCL) |  |  | 40.23 | Placed at Estimation Folder Annex at Sl No. 62_PHC
| Nayagada | Banigochha | PHC | PHC 24x7 Building | 2022-24 | 200 |  |  | 120 | 0 | 120 |  | Completed with funding from State budget
33 | Nayagada | Kujamendhi | PHC | PHC 24x7 Building | 2022-24 | 200 |  |  | 120 |  | 120 |  | Estimate submitted for sanctioned of additional fund |  |  | 24
34 | Nayagada | Kantilo | PHC | PHC 24x7 Building | 2022-24 | 200 |  | 296.87 | 120 |  | 120 |  | Tender invited |  |  | 53.061 | Placed at Estimation Folder Sl No. 67 A_PHC
35 | Nuapada | Sunabeda-Nuapada | PHC | PHC 24x7 Building | 2022-24 | 200 | 219.58 |  | 175.66 | 0 | 175.66 | 190 | Completed |  |  | 43.92
36 | Sambalpur | Padiabahal | PHC | PHC 24x7 Building | 2022-24 | 200 | 218.46 |  | 174.77 | 0 | 174.77 | 196.67 | Completed & Handed over | 2024-03-25 |  | 43.69
37 | Sambalpur | Kusumi-Kuntara | PHC | PHC 24x7 Building | 2022-24 | 200 |  | 218.52 | 174.8 | 0 | 174.8 | 196.72 | Civil Work Completed. E.I. and P.H. Work Under Progress | 2025-12-30 |  | 43.72 | Placed at Estimation Folder Annex at Sl No.84_PHC
38 | Sambalpur | Tureiniktimal | PHC | PHC 24x7 Building | 2022-24 | 200 | 218.52 |  | 174.82 | 0 | 174.82 | 196.72 | Civil Work Completed. E.I. and P.H. Work Under Progress | 2025-12-30 |  | 43.7
39 | Sonpur | Mahadevpali | PHC | PHC 24x7 Building | 2022-24 | 200 |  | 219.25 | 175.2 | 0 | 175.2 | 109.63 | completed and Handed over | 25.03.2024 |  | 44.05 | Placed at Estimation Folder Annex at Sl No.85_PHC
40 | Sonpur | Sankara | PHC | PHC 24x7 Building | 2022-24 | 200 |  | 219.38 | 175.2 | 0 | 175.2 | 153.57 | completed and Handed over | 25.03.2024 |  | 44.18 | Placed at Estimation Folder Annex at Sl No.86_PHC
41 | Sonpur | Bhimtikira | PHC | PHC 24x7 Building | 2022-24 | 200 |  | 219.13 | 175.2 | 0 | 175.2 | 109.57 | completed | 25.03.2024 |  | 43.93 | Placed at Estimation Folder Annex at Sl No.87_PHC
42 | Sonpur | Kamsara | PHC | PHC 24x7 Building | 2022-24 | 200 |  | 219.39 | 175.2 | 0 | 175.2 | 153.58 | completed and Handed over | 25.03.2024 |  | 44.19 | Placed at Estimation Folder Annex at Sl No.88_PHC
43 | Sonpur | Pua | PHC | PHC 24x7 Building | 2022-24 | 200 |  | 219.28 | 175.2 | 0 | 175.2 | 153.5 | completed | 25.03.2024 |  | 44.08 | Placed at Estimation Folder Annex at Sl No.89_PHC
44 | Sonpur | Sindhol | PHC | PHC 24x7 Building | 2022-24 | 200 |  | 219.48 | 175.2 | 0 | 175.2 | 153.63 | completed and Handed over | 25.03.2024 |  | 44.28 | Placed at Estimation Folder Annex at Sl No.91_PHC
45 | Sonpur | Jaloi | PHC | PHC 24x7 Building | 2022-24 | 200 | 219 |  | 175.2 | 0 | 175.2 | 109.34 | colour work in progress | 20.10.2025 |  | 43.8
Total 24x7 PHC | [5 empty] | 9200 | 6412.58 | 2946.06 | 7147.53 | 612.82 | 7760.35 | 5164.07 |  | 321501 | 0 | 1917.509
1 | Anugola | Purunakote | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 77.6 | 0 | 77.6 | 29.1 | Colouring work inprogress | 18.10.2025 |  | 19.4
2 | Baragada | Ambabhana | PHC | PHC Day Care Building | 2022-24 | 97 | 106.47 |  | 48 | 0 | 48 | 31.94 | Completed |  |  | 58.47
3 | Baragada | Larambha | PHC | PHC Day Care Building | 2022-24 | 97 | 106.66 |  | 48 | 0 | 48 | 32 | Completed |  |  | 58.66
4 | Baragada | Birmal | PHC | PHC Day Care Building | 2022-24 | 97 | 106.24 |  | 48 | 0 | 48 | 31.87 | Completed |  |  | 58.24
5 | Baragada | Kumbhari | PHC | PHC Day Care Building | 2022-24 | 97 | 106.69 |  | 48 | 0 | 48 | 32 | Completed |  |  | 58.69
6 | Baragada | Dahita | PHC | PHC Day Care Building | 2022-24 | 97 | 105.56 |  | 48 | 0 | 48 | 31.81 | Completed |  |  | 57.56
7 | Balangir | Duduka | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 77.6 | 0 | 77.6 | 97 | Completed and handedover | 09.12.2023 |  | 19.4
8 | Balangir | Roth | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 77.6 | 0 | 77.6 | 97 | Completed and handedover | 09.12.2023 |  | 19.4
9 | Balangir | Chulifunka | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 77.6 | 0 | 77.6 | 97 | Completed and handedover | 01.09.2023 |  | 19.4
10 | Balangir | Mandal | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 77.6 | 0 | 77.6 | 97 | Completed and handedover | 02.08.2023 |  | 19.4
11 | Balangir | Bandhpara | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 77.6 | 0 | 77.6 | 97 | Completed and handedover | 01.09.2023 |  | 19.4
12 | Balangir | Harisankar | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 77.6 | 0 | 77.6 | 97 | Completed and handedover | 30.08.2023 |  | 19.4
13 | Balangir | Dhandamunda | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 77.6 | 0 | 77.6 | 97 | Completed and handedover | 01.09.2023 |  | 19.4
14 | Balangir | Badimunda | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 77.6 | 0 | 77.6 | 97 | Completed and handedover | 01.09.2023 |  | 19.4
15 | Balangir | Patrapali | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 77.6 | 0 | 77.6 | 97 | Completed and handedover | 01.09.2023 |  | 19.4
16 | Balangir | Bhainsa | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 77.6 | 0 | 77.6 | 97 | Completed and handedover | 22.12.2023 |  | 19.4
17 | Balangir | Solabandha | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 77.6 | 0 | 77.6 | 97 | Completed and handedover | 22.12.2023 |  | 19.4
18 | Balangir | Belgaon | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 77.6 | 0 | 77.6 | 94 | Completed and handedover | 05.09.2023 |  | 19.4
19 | Balangir | Bhatipada | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 77.6 | 0 | 77.6 | 97 | Completed and handedover | 30.01.2024 |  | 19.4
20 | Boudh | Charichak | PHC | PHC Day Care Building | 2022-24 | 97 |  | 141.7 | 48 |  | 48 |  | Tender Under scrutiny |  |  | 28.11 | Placed at Estimation Folder Annex at Sl No. 18 _PHC
21 | Boudh | Ghantapada | PHC | PHC Day Care Building | 2022-24 | 97 |  | 139.45 | 48 |  | 48 |  | Tender Under scrutiny |  |  | 27.435 | Placed at Estimation Folder Annex at Sl No. 19 _PHC
22 | Boudh | Palasaguda | PHC | PHC Day Care Building | 2022-24 | 97 |  | 141.42 | 48 |  | 48 |  | Tender Under scrutiny |  |  | 28.026 | Placed at Estimation Folder Annex at Sl No. 20 _PHC
23 | Kataka | Khuntuni | PHC | PHC Day Care Building | 2022-24 | 97 | 125 |  | 48 | 62 | 110 | 33 | Completed & Handed over |  |  | 15
| Kataka | Badanuaput | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 48 | 62 |  | 52 | Land not available | 30.10.2025 | in To be dropped list |  | Dropped
24 | Kataka | Mundali | PHC | PHC Day Care Building | 2022-24 | 97 | 125 |  | 48 | 62 | 110 | 40 | Finishing Work in Progress | 30.12.2025 |  | 15
25 | Kataka | Handibhanga | PHC | PHC Day Care Building | 2022-24 | 120 |  |  | 48 |  | 48 | 40 | To be retendered, Reporoposed | 30.12.2025 | Reproposed | 30
26 | Kataka | Kundipadia | PHC | PHC Day Care Building | 2022-24 | 97 | 124.85 |  | 48 | 62 | 110 | 45 | Finishing Work in Progress | 31.10.2025 |  | 14.85
27 | Kataka | Asureswar | PHC | PHC Day Care Building | 2022-24 | 97 | 124.91 |  | 48 | 62 | 110 | 33 | Finishing Work in Progress | 31.12.2025 |  | 14.91
28 | Kataka | Kishorenagar | PHC | PHC Day Care Building | 2022-24 | 97 | 124.86 |  | 48 | 62 | 110 | 35.38 | Ground Floor Roof level. | 31.12.2025 |  | 4.458
29 | Kataka | Sagar | PHC | PHC Day Care Building | 2022-24 | 97 | 124.94 |  | 48 | 62 | 110 | 0 | Plinth Level | 30.12.2025 |  | 4.482
30 | Kataka | Brahmapura | PHC | PHC Day Care Building | 2022-24 | 97 | 125 |  | 48 | 62 | 110 | 0 | Foundation Work in Progress |  |  | 4.5
31 | Debagada | Reamal | PHC | PHC Day Care Building | 2022-24 | 97 | 106 |  | 84.8 | 0 | 84.8 | 90 | Completed | 2025-08-29 |  | 21.2
32 | Debagada | Kansar | PHC | PHC Day Care Building | 2022-24 | 97 | 105.22 |  | 84.18 | 0 | 84.18 | 100 | Completed & handed over | 30.10.2024 |  | 21.04
33 | Dhenkanal | Barua | PHC | PHC Day Care Building | 2022-24 | 97 |  | 116.9166 | 48 | 0 | 48 | 35.07 | completed |  |  | 68.9166 | Placed at Estimation Folder Annex at Sl No.30_PHC
34 | Dhenkanal | Guneibili | PHC | PHC Day Care Building | 2022-24 | 97 |  | 117.1846 | 48 | 0 | 48 | 35.15 | completed |  |  | 69.1846 | Placed at Estimation Folder Sl No. 34 _PHC
35 | Dhenkanal | Muktapasi | PHC | PHC Day Care Building | 2022-24 | 97 |  | 124.9998 | 48 | 0 | 48 | 0 | Roof Slab to be cast | 31.12.2025 |  | 53.8998 | Placed at Estimation Folder Sl No. 36 _PHC
36 | Dhenkanal | Dadaraghati | PHC | PHC Day Care Building | 2022-24 | 97 |  | 102.47 | 48 | 0 | 48 | 25.68 | Finishing work in Progress | 31.10.2025 |  | 54.47 | Placed at Estimation Folder Annex at Sl No. 31 _PHC
37 | Dhenkanal | Paikapurunakote | PHC | PHC Day Care Building | 2022-24 | 97 |  | 101.86 | 48 | 0 | 48 | 26.85 | Finishing work in Progress | 31.10.2025 |  | 53.86 | Placed at Estimation Folder Sl No. 33 _PHC
38 | Dhenkanal | Kantiokateni | PHC | PHC Day Care Building | 2022-24 | 97 |  | 100.74 | 48 | 0 | 48 | 30.49 | Finishing work in Progress | 31.12.2025 |  | 52.74 | Placed at Estimation Folder Sl No. 35 _PHC
39 | Dhenkanal | Pingua | PHC | PHC Day Care Building | 2022-24 | 97 |  | 100.65 | 48 | 0 | 48 | 25.72 | Finishing work in Progress | 31.12.2025 |  | 52.65 | Placed at Estimation Folder Sl No. 37 _PHC
40 | Dhenkanal | Bedapada | PHC | PHC Day Care Building | 2022-24 | 97 |  | 102.03 | 48 |  | 48 |  | Lay out to be given |  |  | 16.209 | Placed at Estimation Folder Sl No. 32 _PHC
41 | Gajapati | Loba | PHC | PHC Day Care Building | 2022-24 | 97 | 106.69 |  | 48 | 0 | 48 | 59.94 | Plastering work in progress | 30.10.2025 |  | 41.083
42 | Gajapati | Khandava | PHC | PHC Day Care Building | 2022-24 | 97 | 106.69 |  | 48 | 0 | 48 | 77.07 | EI Ph in progress | 1.12.2025 |  | 58.69
43 | Gajapati | Namanguda | PHC | PHC Day Care Building | 2022-24 | 97 | 106.69 |  | 48 | 0 | 48 | 0 | Foundation work in progress | 30.10.2025 |  | 17.607
| Ganjam | Padmanavpur | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 48 | 49 |  | 75.72 | Work not Started Due to Land Issue, Land not available |  | in To be dropped list |  | Dropped
44 | Ganjam | Dayanidhipur | PHC | PHC Day Care Building | 2022-24 | 97 |  | 142.97 | 48 |  | 48 |  | Tender to be invited |  |  | 28.491 | Placed at Estimation Folder Annex at Sl No. 45 _PHC
45 | Jagatsinghpur | DASABATIA | PHC | PHC Day Care Building | 2022-24 | 97 |  | 155.122 | 48 | 0 | 48 |  | Plinth Level | 30.11.2026 |  | 32.1366 | Placed at Estimation Folder Annex at Sl No. 46 _PHC
46 | Jagatsinghpur | TARASAHI | PHC | PHC Day Care Building | 2022-24 | 97 |  | 157 | 48 | 0 | 48 |  | Plinth Level | 30.11.2026 |  | 32.7 | Placed at Estimation Folder Annex at Sl No. 47 _PHC
47 | Jagatsinghpur | Bagalpur | PHC | PHC Day Care Building | 2022-24 | 97 |  | 157 | 48 | 0 | 48 |  | Plinth Level | 30.11.2026 |  | 32.7 | Placed at Estimation Folder Annex at Sl No. 48 _PHC
48 | Jagatsinghpur | Kolar | PHC | PHC Day Care Building | 2022-24 | 97 |  | 157 | 48 | 0 | 48 |  | Plinth Level | 30.11.2026 |  | 32.7 | Placed at Estimation Folder Annex at Sl No. 49 _PHC
49 | Jharsuguda | Bhadimal | PHC | PHC Day Care Building | 2022-24 | 97 | 142.97 |  | 48 | 62 | 110 |  | Layout to be given after laying of Foundation stone |  |  | 9.891
| Jharsuguda | Adhapara | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 48 | 62 |  |  | Site Not Available |  | in To be dropped list |  | Dropped
50 | Kandhamal | Possara | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 77.6 | 0 | 77.6 | 96.25 | Completed & Handed Over |  |  | 19.4
51 | Kandhamal | Naringijhola | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 77.6 | 0 | 77.6 | 96.24 | Completed & Handed Over |  |  | 19.4
52 | Kandhamal | Sunagaon | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 77.6 | 0 | 77.6 | 96.78 | Completed & Handed Over |  |  | 19.4
53 | Kandhamal | Sikarmaha | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 77.6 | 0 | 77.6 | 29 | Finishing Stage | 31.10.2025 |  | 19.4
54 | Kandhamal | Khamankhole | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 77.6 | 0 | 77.6 | 13 | Roof Level | 31.10.2025 |  | 19.4
55 | Kandhamal | Srirampur | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 48 | 0 | 48 | 13 | Roof Level | 31.10.2025 |  | 49
56 | Kandhamal | Lankagada | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 48 | 0 | 48 | 13 | Roof Level | 31.10.2025 |  | 49
57 | Kandhamal | Sugudabadi | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 77.6 | 0 | 77.6 |  | Foundation Level | 31.12.2025 |  | 5.82
58 | Kendrapada | Korua | PHC | PHC Day Care Building | 2022-24 | 97 | 142.61 |  | 48 | 62 | 110 | 31.53 | Roof Level | 31.12..2025 |  | 32.61
59 | Kendrapada | Tendakuda | PHC | PHC Day Care Building | 2022-24 | 97 | 142.61 |  | 48 | 62 | 110 | 21 | G.F Lintel Level | 15.12.2025 |  | 9.783
60 | Kendrapada | Ayaba | PHC | PHC Day Care Building | 2022-24 | 97 | 142.96 |  | 48 | 62 | 110 | 0 | Foundation work | 20.02.2026 |  | 9.888
61 | Kendrapada | Pailo | PHC | PHC Day Care Building | 2022-24 | 97 | 106.35 |  | 48 | 0 | 48 | 0 | Lintel Level | 15.12.2025 |  | 17.505
62 | Kendrapada | Balia | PHC | PHC Day Care Building | 2022-24 | 97 | 142.71 |  | 48 | 62 | 110 |  | work to be strat in a week(Design Received) |  |  | 9.813
63 | Kendrapada | Katana | PHC | PHC Day Care Building | 2022-24 | 97 | 142.71 |  | 48 | 62 | 110 |  | Revised estimate under Preparation ,site finalised |  |  | 9.813
64 | Khordha | Chandaka | PHC | PHC Day Care Building | 2022-24 | 97 | 102 |  | 48 | 0 | 48 | 20.92 | Completed |  |  | 54
| Koraput | Ranigada | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 48 | 58.7 |  | 0 | Contractor not responding, Show cause issued | 30.10.2025 | in To be dropped list |  | Dropped
65 | Malkanagiri | Koikunda | PHC | PHC Day Care Building | 2022-24 | 97 |  | 125 | 48 | 0 | 48 | 36.5 | Finishing stage | 30.11.2025 |  | 53.9 | Placed at Estimation Folder Annex at Sl No. 57_PHC
66 | Malkanagiri | Padmagiri | PHC | PHC Day Care Building | 2022-24 | 97 |  | 125 | 48 | 0 | 48 | 50 | Finishing stage | 30.11.2025 |  | 53.9 | Placed at Estimation Folder Annex at Sl No. 60_PHC
67 | Malkanagiri | Govindapalli | PHC | PHC Day Care Building | 2022-24 | 97 |  | 125 | 48 |  | 48 |  | Layout given |  |  | 23.1 | Placed at Estimation Folder Annex at Sl No. 58_PHC
68 | Malkanagiri | Mudulipada | PHC | PHC Day Care Building | 2022-24 | 97 |  | 125 | 48 |  | 48 |  | Layout to be given Shifted from Badapada to Mudulipada |  |  | 23.1 | Placed at Estimation Folder Annex at Sl No-104 Badapada PHC Diverted to Mudulipada
69 | Mayurbhanj | Suliapada | PHC | PHC Day Care Building | 2022-24 | 97 |  | 128 | 48 | 62 | 110 | 30 | Finishing work in progress | 30.10.2025 |  | 18 | Placed at Estimation Folder Annex at Sl No. 64_PHC
70 | Mayurbhanj | Tangabila | PHC | PHC Day Care Building | 2022-24 | 97 | 125 |  | 48 | 62 | 110 |  | A/A Done(Tender to be invited) |  |  | 4.5
71 | Mayurbhanj | Guhaldangiri | PHC | PHC Day Care Building | 2022-24 | 97 | 125 |  | 48 | 62 | 110 |  | A/A Done(Tender to be invited) |  |  | 4.5
72 | Nayagada | Balugaon | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 77.6 | 0 | 77.6 | 29 | Completed |  |  | 19.4
73 | Nayagada | Itamati | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 77.6 | 0 | 77.6 | 29 | Completed |  |  | 19.4
74 | Nayagada | Kaliakaprasad | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 77.6 | 0 | 77.6 | 29 | Completed |  |  | 19.4
75 | Nayagada | Kajalaipalli | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 77.6 | 0 | 77.6 | 87.3 | Completed |  |  | 19.4
76 | Nayagada | Komanda | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 77.6 | 0 | 77.6 | 87.3 | Completed |  |  | 19.4
77 | Nayagada | Darpanarayanpur | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 48 | 0 | 48 | 18.23 | Completed |  |  | 49
78 | Nayagada | Majhikhanda | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 77.6 | 0 | 77.6 | 28.45 | Finishing | 2025-12-30 |  | 19.4
79 | Nayagada | Mayurjhalia | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 48 | 0 | 48 | 52.48 | Finishing | 2025-12-30 |  | 49
80 | Nayagada | Nimani | PHC | PHC Day Care Building | 2022-24 | 97 | 124.81 |  | 48 | 62 | 110 | 37.44 | Roof level | 2025-12-30 |  | 14.81
81 | Nuapada | Bainsadhini | PHC | PHC Day Care Building | 2022-24 | 97 | 106.07 |  | 47.27 | 58.07 | 105.34 | 47.27 | Plastering Completed | 30.10.2025 |  | 0.73
82 | Puri | Satasankha | PHC | PHC Day Care Building | 2022-24 | 97 |  | 103.84 | 48 | 0 | 48 | 104 | Completed but not handing over due to External EI and periphery development work to be done |  |  | 39.088 | Placed at Estimation Folder Sl No-126 Satasankha PHC
83 | Puri | Bantilo | PHC | PHC Day Care Building | 2022-24 | 97 |  | 105.84 | 48 | 0 | 48 | 85 | Finishing works in progress | 30.10.25 |  | 40.488 | Placed at Estimation Folder Sl No-135 Bantilo PHC
84 | Puri | Harirajapur | PHC | PHC Day Care Building | 2022-24 | 97 |  | 102.77 | 48 | 0 | 48 | 66 | Finishing works in progress | 30.10.25 |  | 38.339 | Placed at Estimation Folder Sl No-128 Harirajpur PHC
85 | Puri | Badatara | PHC | PHC Day Care Building | 2022-24 | 97 |  | 102.5 | 48 | 0 | 48 | 27.5 | Finishing works in progress | 30.10.25 |  | 38.15 | Placed at Estimation Folder Sl. no 129 - PHC Badatara
86 | Puri | Titipa | PHC | PHC Day Care Building | 2022-24 | 97 |  | 105.3 | 48 | 0 | 48 |  | Foundation works in progress | 30.11.2026 |  | 17.19 | Placed at Estimation Folder Sl No-130 titipa PHC
| Puri | KHANDAKAI | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 48 |  |  |  | encroachment by local body issued letter to the tahasildhar for eviction, Buildingless PHC |  | in To be dropped list |  | Dropped
87 | Puri | Kamakantia | PHC | PHC Day Care Building | 2022-24 | 97 |  | 103.3 | 48 |  | 48 |  | design to be furnished |  |  | 16.59 | Placed at Estimation Folder Sl No-132 Kamakantia
| Puri | Chalisbatia | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 48 |  |  |  | site not available |  | in To be dropped list |  | Dropped
88 | Rayagada | Durgi | PHC | PHC Day Care Building | 2022-24 | 97 |  | 106.69 | 48 | 0 | 48 | 30 | ei work in progress | 31.10.2025 |  | 41.083 | Placed at Estimation Folder Annex at SL No 137 PHC Durgi
89 | Sambalpur | Paramanpur | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 48 | 0 | 48 | 47.59 | Finishing Work Under Progress | 2025-10-30 |  | 34.3
90 | Sambalpur | Girishchandrapur | PHC | PHC Day Care Building | 2022-24 | 97 | 100 |  | 48 | 0 | 48 | 30 | Finishing Work Under Progress | 2025-10-30 |  | 34.3
91 | Sambalpur | Kadaligarh | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 48 | 0 | 48 | 22 | Finishing Work Under Progress | 2025-11-30 |  | 34.3
92 | Sonpur | Murusundi | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 77.6 | 0 | 77.6 | 34.37 | completed and Handed over | 26.11.2023 |  | 19.4
93 | Sonpur | Beheramal | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 77.6 | 0 | 77.6 | 35.85 | Completed | 26.11.2023 |  | 19.4
94 | Sonpur | Digasara | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 77.6 | 0 | 77.6 | 34.56 | Completed | 13.08.2023 |  | 19.4
95 | Sonpur | Sukha | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 77.6 | 0 | 77.6 | 66.34 | Completed | 26.11.2023 |  | 19.4
96 | Sonpur | Bankighirdi | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 77.6 | 0 | 77.6 | 7.65 | Finishing work in progress | 30.10.2025 |  | 13.58
97 | Sonpur | Haradakhole | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 77.6 | 0 | 77.6 | 22.72 | civil work and PH completed, EI work in progress | 10.10.2025 |  | 13.58
98 | Sonpur | Menda | PHC | PHC Day Care Building | 2022-24 | 97 |  |  | 77.6 | 0 | 77.6 | 36.44 | EI fittings work is pending | 10.10.2025 |  | 13.58
Total Day Care PHC | [5 empty] | 10111 | 3583.27 | 3416.7529 | 6041.05 | 1343.77 | 6865.12 | 3949.5 |  | 321872 | 0 | 2707.4996
Grand Total PHC 2022-24 | [5 empty] | 19311 | 9995.85 | 10378.003 | 13188.58 | 1956.59 | 14625.47 | 9113.57 |  |  |  | 4625.0086
0

## Annex-6-SC 2022-24
Status of Civil Construction under NHM PIP Works approved during 2022-24, Odisha
Sl. No. | Name of the District | NameoftheFacility | Type of Facility | Name of the work | Year of Sanction of works | Total Project Cost approved (in Rs. Lakhs) | Revised cost in 2024-26 (In lakh) | Revised cost in 2026-27 (In lakh) | Amount Sanctioned till 2025-26 (Rs in Lakh) | Approved in Supplementary PIP 25-26 | Total Approval | Expenditure till August 2025 (Rs in Lakhs) | Physical Status of the work till August 2025 | Estimated year / month of completion of work |  | Fund Approved in 2026-27 (Rs. In Lakhs) | Remarks
1 | Anugola | Golabandha. | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 0 | Plinth level | 30.12.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.5_SC
2 | Anugola | Kulad | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 0 | F F roof level | 30.12.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.2_SC
3 | Anugola | Kurudol | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 12.1824 | Tile work inprogress | 30.12.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.3_SC
4 | Anugola | Mahidharpur | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 0 | plastering work in progress | 30.12.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.7_SC
5 | Anugola | Santrapur | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 0 | F F lintel level | 30.12.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.6_SC
6 | Anugola | Tubey | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 12.045 | Tile work inprogress | 30.12.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.4_SC
| Baleshwar | Ambakuduchi | SC | New Building for Existing SCs | 2022-24 | 46 |  |  | 46 |  | 46 |  | Land Issue |  | To be dropped
7 | Baleshwar | Bishnupur | SC | New Building for Existing SCs | 2022-24 | 46 | 49.96 | 54.99 | 46 |  | 46 |  | Land Finalised |  |  | 8.99
| Baleshwar | Chafla | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 | 4 | 50 |  | Land Issue |  | To be dropped
8 | Baleshwar | Jamudihi | SC | New Building for Existing SCs | 2022-24 | 46 | 49.98 |  | 46 |  | 46 |  | Land Issue Finalised |  |  | 3.98
| Baleshwar | Kadrayan | SC | New Building for Existing SCs | 2022-24 | 46 |  |  | 46 |  | 46 |  | Land Issue |  | To be dropped
9 | Baleshwar | Kasipada | SC | New Building for Existing SCs | 2022-24 | 46 | 49.99 |  | 46 |  | 46 |  | Land Finalised |  |  | 3.99
10 | Baleshwar | Nabara | SC | New Building for Existing SCs | 2022-24 | 46 | 49.99 |  | 46 |  | 46 |  | Land Finalised |  |  | 3.99
| Baleshwar | Putura | SC | New Building for Existing SCs | 2022-24 | 46 |  |  | 46 |  | 46 |  | Land Issue |  | To be dropped
| Baleshwar | Routpada | SC | New Building for Existing SCs | 2022-24 | 46 | 49.99 |  | 46 | 3.99 | 49.99 |  | Land Issue |  | To be dropped
11 | Baleshwar | Tentulia | SC | New Building for Existing SCs | 2022-24 | 46 | 48.46 | 48.48 | 46 |  | 46 | 0 | GF Window Sill Level | 24.10.2025 |  | 2.48
12 | Baragada | Bagbadi | SC | New Building for Existing SCs | 2022-24 | 46 | 55 |  | 46 |  | 46 | 23.12 | finishing stage | 31.12.2025 |  | 9
13 | Baragada | BARGAON | SC | New Building for Existing SCs | 2022-24 | 46 | 55 |  | 46 |  | 46 | 26 | In finishing stage | 31.10.2025 |  | 9
14 | Baragada | Bhointara | SC | New Building for Existing SCs | 2022-24 | 46 | 55 |  | 46 |  | 46 |  | Dismantling work completed |  |  | 9
15 | Baragada | Budapali | SC | New Building for Existing SCs | 2022-24 | 46 | 55 |  | 46 |  | 46 | 26.61 | In finishing stage | 31.10.2025 |  | 9
| Baragarh | Jharpali | SC | New Building for Existing SCs | 2022-24 | 46 | 55 |  | 55 |  | 55 |  | Agreement to be resigned, due to land dispute. |  | To be dropped
16 | Baragada | Kharmunda | SC | New Building for Existing SCs | 2022-24 | 46 | 55 |  | 46 |  | 46 | 16 | In finishing stage | 31.12.2025 |  | 9
17 | Baragada | Kumbho | SC | New Building for Existing SCs | 2022-24 | 46 | 55 |  | 46 |  | 46 |  | Aggrement done , |  |  | 9
18 | Baragada | Launsara | SC | New Building for Existing SCs | 2022-24 | 46 | 55 |  | 46 |  | 46 | 25 | In finishing stage | 31.12.2025 |  | 9
19 | Baragada | Lenda | SC | New Building for Existing SCs | 2022-24 | 46 | 55 |  | 46 |  | 46 | 0 | 1st floor roof cast | 31.12.2025 |  | 9
20 | Baragada | Patkulunda | SC | New Building for Existing SCs | 2022-24 | 46 | 55 |  | 46 |  | 46 | 18.38 | In finishing stage | 31.10.2025 |  | 9
21 | Baragada | Rusuda | SC | New Building for Existing SCs | 2022-24 | 46 | 55 |  | 46 |  | 46 | 21 | In finishing stage | 31.12.2025 |  | 9
22 | Baragada | Talsirgida | SC | New Building for Existing SCs | 2022-24 | 46 | 55 |  | 46 |  | 46 | 22 | In finishing stage | 30.11.2025 |  | 9
23 | Baragada | Tejagola | SC | New Building for Existing SCs | 2022-24 | 46 | 55 |  | 46 |  | 46 | 22 | In finishing stage | 31.10.2025 |  | 9
24 | Baragada | Tope | SC | New Building for Existing SCs | 2022-24 | 46 | 55 |  | 46 |  | 46 |  | Aggrement done |  |  | 9
| Bhadrak | Haladharbinda | SC | New Building for Existing SCs | 2022-24 | 46 |  |  | 46 |  | 46 |  | Encroachment to be evacuated from the proposed site |  | To be dropped
25 | Bhadrak | Jitanga | SC | New Building for Existing SCs | 2022-24 | 46 |  | 50.6 | 46 |  | 46 | 39.5 | Completed |  |  | 4.6 | Placed at Estimation Folder Annex at Sl No.9_SC
| Bhadrak | Rajmukundpur | SC | New Building for Existing SCs | 2022-24 | 46 |  |  | 46 |  | 46 |  | Site identified but Local dispute during layout |  | To be dropped
26 | Balangir | Amurla | SC | New Building for Existing SCs | 2022-24 | 46 |  | 49.96 | 46 |  | 46 | 49.96 | Completed and handedover | 22.12.2023 |  | 3.96
27 | Balangir | Badbandh | SC | New Building for Existing SCs | 2022-24 | 46 |  | 49.95 | 46 |  | 46 | 49.95 | Completed and handedover | 22.12.2023 |  | 3.95 | Placed at Estimation Folder Annex at Sl No.20_SC
28 | Balangir | Desil | SC | New Building for Existing SCs | 2022-24 | 46 |  | 49.96 | 46 |  | 46 | 49.96 | Completed and handedover | 22.12.2023 |  | 3.96 | Placed at Estimation Folder Annex at Sl No.22_SC
29 | Balangir | Gourgoth | SC | New Building for Existing SCs | 2022-24 | 46 |  | 49.95 | 46 |  | 46 | 49.95 | Completed and handedover | 09.02.2024 |  | 3.95 | Placed at Estimation Folder Annex at Sl No.18_SC
30 | Balangir | Icchapada | SC | New Building for Existing SCs | 2022-24 | 46 |  | 49.96 | 46 |  | 46 | 46.05 | Completed and handedover | 22.12.2023 |  | 3.96 | Placed at Estimation Folder Annex at Sl No.25_SC
31 | Balangir | Rugudipali | SC | New Building for Existing SCs | 2022-24 | 46 |  | 49.95 | 46 |  | 46 | 49.95 | Completed and handedover | 09.02.2024 |  | 3.95 | Placed at Estimation Folder Annex at Sl No.19_SC
32 | Balangir | Sagadghat | SC | New Building for Existing SCs | 2022-24 | 46 |  | 49.96 | 46 |  | 46 | 42.23 | Completed and handedover | 22.12.2023 |  | 3.96
33 | Balangir | Sihini | SC | New Building for Existing SCs | 2022-24 | 46 |  | 49.96 | 46 |  | 46 | 49.96 | Completed and handedover | 22.12.2023 |  | 3.96
| Boudh | Podapada Ghantapa | SC | New Building for Existing SCs | 2022-24 | 46 |  |  | 46 |  | 46 |  | Land issue, agreement cancelled |  | To be dropped
34 | Kataka | Banahara | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 0 | Foundation Stage | 31.07.2026 |  | 9
| Cuttack | Baragodia | SC | New Building for Existing SCs | 2022-24 | 46 |  |  | 46 |  | 46 |  | Work completed & handedover |  | To be dropped
| Cuttack | Betei | SC | New Building for Existing SCs | 2022-24 | 46 |  |  | 46 |  | 46 |  | Land issue |  | To be dropped
35 | Kataka | Biswalpada | SC | New Building for Existing SCs | 2022-24 | 46 |  | 54.95 | 46 |  | 46 | 16.5 | Ground Floor Roof Cast | 31.12.2025 |  | 8.95
36 | Kataka | Gangeswar | SC | New Building for Existing SCs | 2022-24 | 46 |  | 54.99 | 46 |  | 46 | 0 | Foundation Work in Progress | 31.12.2025 |  | 8.99
37 | Kataka | Kurang Pradhan | SC | New Building for Existing SCs | 2022-24 | 46 |  | 54.98 | 46 |  | 46 |  | To be retendered |  |  | 8.98
38 | Kataka | Mundamunan | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 32 | civil completed EI & PH work in progress | 31.12.2025 |  | 9
| Cuttack | Taradapada | SC | New Building for Existing SCs | 2022-24 | 46 |  |  | 46 |  | 46 |  |  |  | To be dropped
39 | Kataka | Usuma | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 0 | GF roof level | 31.12.2025 |  | 9
40 | Dhenkanal | Arakhapal | SC | New Building for Existing SCs | 2022-24 | 46 | 50.4 | 54.9533 | 46 |  | 46 | 16.49 | Civil work completed,EI & PH work in progress | 31.10.2025 |  | 8.9533 | Placed at Estimation Folder Annex at Sl No. Dhenkanal
41 | Dhenkanal | Badasuanlo | SC | New Building for Existing SCs | 2022-24 | 46 | 50.48 | 54.3769 | 46 |  | 46 | 1450 | Finishing work in Progress | 31.10.2025 |  | 8.3769 | Placed at Estimation Folder Annex at Sl No. Dhenkanal
42 | Dhenkanal | Balabhadrapur. | SC | New Building for Existing SCs | 2022-24 | 46 | 49.8 | 54.912 | 46 |  | 46 | 15.46 | Finishing work in Progress | 31.10.2025 |  | 8.912
43 | Dhenkanal | Bausapokhari | SC | New Building for Existing SCs | 2022-24 | 46 | 50.29 | 54.7621 | 46 |  | 46 | 16.43 | F F Lintel level | 31.10.2025 |  | 8.7621
44 | Dhenkanal | Bega | SC | New Building for Existing SCs | 2022-24 | 46 | 49.83 | 54.9248 | 46 |  | 46 | 16.48 | Completed | 31.10.2025 |  | 8.9248
45 | Dhenkanal | Bhaliabol kateni | SC | New Building for Existing SCs | 2022-24 | 46 | 49.82 | 55.0713 | 46 |  | 46 | 16.52 | completed |  |  | 9.0713
46 | Dhenkanal | Bidharpur | SC | New Building for Existing SCs | 2022-24 | 46 | 49.77 | 58.47 | 46 |  | 46 |  | Awaiting for A/A at state level |  |  | 12.47
47 | Dhenkanal | Brahmanipal | SC | New Building for Existing SCs | 2022-24 | 46 | 49.82 | 54.6711 | 46 |  | 46 | 15.23 | Completed | 31.10.2025 |  | 8.6711
48 | Dhenkanal | Dayanbil | SC | New Building for Existing SCs | 2022-24 | 46 | 50.13 | 54.0134 | 46 |  | 46 | 15.38 | Civil work completed,EI & PH work in progress | 31.10.2025 |  | 8.0134 | Placed at Estimation Folder Annex at Sl No. Dhenkanal
49 | Dhenkanal | Goradia | SC | New Building for Existing SCs | 2022-24 | 46 | 50.28 | 54.9472 | 46 |  | 46 | 14.99 | Civil work completed,EI & PH work in progress | 31.10.2025 |  | 8.9472 | Placed at Estimation Folder Annex at Sl No. Dhenkanal
50 | Dhenkanal | Gulehi | SC | New Building for Existing SCs | 2022-24 | 46 | 49.88 | 54.4186 | 46 |  | 46 | 15.04 | Finishing work in Progress | 31.10.2025 |  | 8.4186 | Placed at Estimation Folder Annex at Sl No. Dhenkanal
51 | Dhenkanal | Kaimati | SC | New Building for Existing SCs | 2022-24 | 46 | 49.85 | 55.1087 | 46 |  | 46 | 15.93 | Civil work completed,EI & PH work in progress | 31.10.2025 |  | 9.1087 | Placed at Estimation Folder Annex at Sl No. Dhenkanal
52 | Dhenkanal | Kaluria | SC | New Building for Existing SCs | 2022-24 | 46 | 50.26 | 55.1643 | 46 |  | 46 | 16.1 | Completed | 31.10.2025 |  | 9.1643 | Placed at Estimation Folder Annex at Sl No. Dhenkanal
53 | Dhenkanal | Kangeilo | SC | New Building for Existing SCs | 2022-24 | 46 | 50.37 | 54.9965 | 46 |  | 46 | 16.5 | Finishing work in Progress | 31.10.2025 |  | 8.9965 | Placed at Estimation Folder Annex at Sl No. Dhenkanal
54 | Dhenkanal | Kankadapal | SC | New Building for Existing SCs | 2022-24 | 46 | 49.75 | 54.9642 | 46 |  | 46 | 7.74 | Lintel level | 2023-24 |  | 8.9642 | Placed at Estimation Folder Annex at Sl No. Dhenkanal
55 | Dhenkanal | Kantioputasahi | SC | New Building for Existing SCs | 2022-24 | 46 | 49.77 | 54.7145 | 46 |  | 46 | 16.41 | Civil work & PH work completed,EI work in progress | 31.10.2025 |  | 8.7145 | Placed at Estimation Folder Annex at Sl No. Dhenkanal
56 | Dhenkanal | Karanda | SC | New Building for Existing SCs | 2022-24 | 46 | 49.49 | 54.5109 | 46 |  | 46 | 16.35 | Completed | 31.10.2025 |  | 8.5109 | Placed at Estimation Folder Annex at Sl No. Dhenkanal
57 | Dhenkanal | Kingol | SC | New Building for Existing SCs | 2022-24 | 46 | 50 | 53.8923 | 46 |  | 46 | 16.17 | Civil work completed,EI & PH work in progress | 31.10.2025 |  | 7.8923 | Placed at Estimation Folder Annex at Sl No. Dhenkanal
58 | Dhenkanal | Koilipangi | SC | New Building for Existing SCs | 2022-24 | 46 | 50.04 | 54.9628 | 46 |  | 46 | 16.49 | completed |  |  | 8.9628 | Placed at Estimation Folder Annex at Sl No. Dhenkanal
59 | Dhenkanal | Kunua | SC | New Building for Existing SCs | 2022-24 | 46 | 50.23 | 54.6402 | 46 |  | 46 | 16.39 | completed |  |  | 8.6402 | Placed at Estimation Folder Annex at Sl No. Dhenkanal
60 | Dhenkanal | Madhapur | SC | New Building for Existing SCs | 2022-24 | 46 | 50.46 | 55.4377 | 46 |  | 46 | 16.63 | Finishing work in Progress | 31.10.2025 |  | 9.4377 | Placed at Estimation Folder Annex at Sl No.1_SC
61 | Dhenkanal | Mahulpal | SC | New Building for Existing SCs | 2022-24 | 46 | 50.12 | 54.3834 | 46 |  | 46 | 16.32 | Finishing work in Progress | 31.10.2025 |  | 8.3834 | Placed at Estimation Folder Annex at Sl No. Dhenkanal
62 | Dhenkanal | Mandar | SC | New Building for Existing SCs | 2022-24 | 46 | 49.54 | 55.3382 | 46 |  | 46 | 13.65 | Completed | 31.10.2025 |  | 9.3382 | Placed at Estimation Folder Annex at Sl No. Dhenkanal
63 | Dhenkanal | Rai Narsingh Pur | SC | New Building for Existing SCs | 2022-24 | 46 | 49.54 | 53.391 | 46 |  | 46 | 16.02 | completed |  |  | 7.391 | Placed at Estimation Folder Annex at Sl No. Dhenkanal
64 | Dhenkanal | Raitala | SC | New Building for Existing SCs | 2022-24 | 46 | 49.74 | 54.8925 | 46 |  | 46 | 16.47 | Civil work completed,EI & PH work in progress | 31.10.2025 |  | 8.8925 | Placed at Estimation Folder Annex at Sl No. Dhenkanal
65 | Dhenkanal | Ratanpur | SC | New Building for Existing SCs | 2022-24 | 46 | 49.95 | 55.2169 | 46 |  | 46 | 15.57 | Civil work completed,EI & PH work in progress | 31.10.2025 |  | 9.2169 | Placed at Estimation Folder Annex at Sl No. Dhenkanal
66 | Dhenkanal | Santhapur | SC | New Building for Existing SCs | 2022-24 | 46 | 49.89 | 54.9715 | 46 |  | 46 | 13.93 | Civil work completed,EI & PH work in progress | 31.10.2025 |  | 8.9715 | Placed at Estimation Folder Annex at Sl No. Dhenkanal
67 | Dhenkanal | Sibalaposi | SC | New Building for Existing SCs | 2022-24 | 46 | 50.47 | 54.3057 | 46 |  | 46 | 15.28 | Finishing work in Progress | 31.10.2025 |  | 8.3057 | Placed at Estimation Folder Annex at Sl No. Dhenkanal
68 | Dhenkanal | Sorisiapada | SC | New Building for Existing SCs | 2022-24 | 46 | 50.12 | 54.9251 | 46 |  | 46 | 10.31 | Finishing work in Progress | 31.10.2025 |  | 8.9251 | Placed at Estimation Folder Annex at Sl No. Dhenkanal
69 | Gajapati | Ajayagada | SC | New Building for Existing SCs | 2022-24 | 46 | 55 |  | 46 |  | 46 |  | Tender open on 26.09.2025 |  |  | 9
70 | Gajapati | Allada | SC | New Building for Existing SCs | 2022-24 | 46 | 55 |  | 46 |  | 46 | 16.5 | Complited , External EI Pending |  |  | 9 | Placed at Estimation Folder Annex at Sl No.67_SC
83 | Gajapati | Antaraba | SC | New Building for Existing SCs | 2022-24 | 46 | 55 |  | 46 |  | 46 | 35.99 | Completed but not Handed Over |  | Work executed out of State plan (Mo sarkar)
71 | Gajapati | B Kalakote | SC | New Building for Existing SCs | 2022-24 | 46 | 55 |  | 46 |  | 46 |  |  |  |  | 9
72 | Gajapati | Badakoturu | SC | New Building for Existing SCs | 2022-24 | 46 | 55 |  | 46 |  | 46 | 0 | Window sill level | 30.12.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.63_SC
73 | Gajapati | Bhuskudi | SC | New Building for Existing SCs | 2022-24 | 46 | 55 |  | 46 |  | 46 | 16.5 | Frame strecture completed , Brick work in progress |  |  | 9 | Placed at Estimation Folder Annex at Sl No.66_SC
74 | Gajapati | Gaiba | SC | New Building for Existing SCs | 2022-24 | 46 | 55 |  | 46 |  | 46 | 16.5 | Finishing work in progress |  |  | 9 | Placed at Estimation Folder Annex at Sl No.68_SC
75 | Gajapati | Gosani | SC | New Building for Existing SCs | 2022-24 | 46 | 55 |  | 46 |  | 46 | 14.5 | Frame strecture completed , Brick work in progress | 30.12.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.64_SC
| Gajapati | Hadubhangi | SC | New Building for Existing SCs | 2022-24 | 46 |  |  | 46 |  | 46 |  | No feasible land |  | To be dropped
76 | Gajapati | Haripur. | SC | New Building for Existing SCs | 2022-24 | 46 | 55 |  | 46 |  | 46 | 0 | Lintel level | 31.10.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.71_SC
77 | Gajapati | Jeeba | SC | New Building for Existing SCs | 2022-24 | 46 | 55 |  | 46 |  | 46 | 16.5 | Finishing work in progress |  |  | 9 | Placed at Estimation Folder Annex at Sl No.69_SC
78 | Gajapati | Jhami | SC | New Building for Existing SCs | 2022-24 | 46 | 55 |  | 46 |  | 46 |  | Agreement done, to be started |  |  | 9
79 | Gajapati | Khandava | SC | New Building for Existing SCs | 2022-24 | 46 | 55 |  | 46 |  | 46 |  | Agreement done, to be started |  |  | 9
80 | Gajapati | Kharasanda | SC | New Building for Existing SCs | 2022-24 | 46 | 55 |  | 46 |  | 46 | 30 | Completed without EI | 30.10.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.65_SC
81 | Gajapati | Koinpur | SC | New Building for Existing SCs | 2022-24 | 46 | 55 |  | 46 |  | 46 |  | LOA issued, to be started |  |  | 9
82 | Gajapati | Linga | SC | New Building for Existing SCs | 2022-24 | 46 | 55 |  | 46 |  | 46 | 10 | Ground floor Roof level | 31.10.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.70_SC
83 | Gajapati | Narayanpur | SC | New Building for Existing SCs | 2022-24 | 46 | 55 |  | 46 |  | 46 | 16.5 | EI Ph in progress |  |  | 9 | Placed at Estimation Folder Annex at Sl No.62_SC
98 | Gajapati | P.Govindpur | SC | New Building for Existing SCs | 2022-24 | 46 | 55 |  | 46 |  | 46 | 16.5 | 1st floor roof level | 1.12.2025 | Work executed out of XVFC (21-22)
99 | Gajapati | Tarangada | SC | New Building for Existing SCs | 2022-24 | 46 | 55 |  | 46 |  | 46 | 0 | 1st floor roof level | 30.3.2026 | Work executed out of XVFC (21-22)
| Gajapati | Vinala | SC | New Building for Existing SCs | 2022-24 | 46 |  |  | 46 |  | 46 |  | No land, Tender cancelled |  | To be dropped
84 | Ganjam | B D Pur | SC | New Building for Existing SCs | 2022-24 | 46 |  | 60.1 | 46 |  | 46 |  | Tender reinvited |  |  | 14.1 | Placed at Estimation Folder Annex at Sl No. 36_SC NS
85 | Ganjam | Barapalli | SC | New Building for Existing SCs | 2022-24 | 46 |  | 60.47 | 46 |  | 46 |  | Tender under scrutiny |  |  | 14.47 | Placed at Estimation Folder Annex at Sl No. 33_SC NS
| Ganjam | Brahmanachai | SC | New Building for Existing SCs | 2022-24 | 46 |  |  | 46 |  | 46 |  | A/A Accorded.Tender not invited due to non availabilty of fund.To be dropped |  | To be dropped
86 | Ganjam | Budurungu | SC | New Building for Existing SCs | 2022-24 | 46 |  | 60.5 | 46 |  | 46 |  | Tender reinvited |  |  | 14.5 | Placed at Estimation Folder Annex at Sl No. 37_SC NS
87 | Ganjam | Dhumakumpa | SC | New Building for Existing SCs | 2022-24 | 46 |  | 59.8 | 46 |  | 46 |  | Tender reinvited |  |  | 13.8 | Placed at Estimation Folder Annex at Sl No. 35_SC NS
88 | Ganjam | Inginathi | SC | New Building for Existing SCs | 2022-24 | 46 |  | 60.36 | 46 |  | 46 |  | Land identified & 2nd time tender called |  |  | 14.36 | Placed at Estimation Folder Annex at Sl No. 34_SC NS
| Ganjam | K Barida | SC | New Building for Existing SCs | 2022-24 | 46 |  |  | 46 |  | 46 |  | Land not finalized |  | To be dropped
89 | Ganjam | Kadapada | SC | New Building for Existing SCs | 2022-24 | 46 |  | 60.5 | 46 |  | 46 |  | Tender re invited |  |  | 14.5 | Placed at Estimation Folder Annex at Sl No. 31_SC NS
90 | Ganjam | Khamarapalli | SC | New Building for Existing SCs | 2022-24 | 46 |  | 60.41 | 46 |  | 46 |  | Land identified & 2nd time tender called |  |  | 14.41 | Placed at Estimation Folder Annex at Sl No. 38_SC NS
91 | Ganjam | Khetamundali | SC | New Building for Existing SCs | 2022-24 | 46 |  | 60.5 | 46 |  | 46 |  | Tender reinvited |  |  | 14.5 | Placed at Estimation Folder Annex at Sl No. 39_SC NS
92 | Ganjam | Kumarpani | SC | New Building for Existing SCs | 2022-24 | 46 |  | 59.94 | 46 |  | 46 |  | Work order issued |  |  | 13.94 | Placed at Estimation Folder Annex at Sl No.78_SC
93 | Ganjam | Kurala | SC | New Building for Existing SCs | 2022-24 | 46 |  | 58.66 | 46 |  | 46 | 0 | Finishing work is in progress | 30.11.2025 |  | 12.66 | Placed at Estimation Folder Annex at Sl No.79_SC
94 | Ganjam | Mantapada | SC | New Building for Existing SCs | 2022-24 | 46 |  | 57.14 | 46 |  | 46 | 0 | Lintel level (GF) | 30.03.2026 |  | 11.14 | Placed at Estimation Folder Annex at Sl No.81_SC
95 | Ganjam | Merikote | SC | New Building for Existing SCs | 2022-24 | 46 |  | 59.48 | 46 |  | 46 |  | Work order issued |  |  | 13.48 | Placed at Estimation Folder Annex at Sl No.80_SC
96 | Ganjam | Nettanga | SC | New Building for Existing SCs | 2022-24 | 46 |  | 60.5 | 46 |  | 46 |  | Land identified & 2nd time tender called |  |  | 14.5 | Placed at Estimation Folder Annex at Sl No. 30_SC NS
97 | Ganjam | Panchabhuti | SC | New Building for Existing SCs | 2022-24 | 46 |  | 60.5 | 46 |  | 46 |  | Tender under scrutiny |  |  | 14.5 | Placed at Estimation Folder Annex at Sl No. 32_SC NS
98 | Ganjam | S Chhachina | SC | New Building for Existing SCs | 2022-24 | 46 |  | 60.48 | 46 |  | 46 | 0 | Ground floor slab casted | 31.03.2026 |  | 14.48 | Placed at Estimation Folder Annex at Sl No.76_SC
99 | Ganjam | Talasara | SC | New Building for Existing SCs | 2022-24 | 46 |  | 60.5 | 46 |  | 46 | 0 | Foundation work in progress | 31.03.26 |  | 14.5 | Placed at Estimation Folder Annex at Sl No.77_SC
100 | Kendrapada | Akhua | SC | New Building for Existing SCs | 2022-24 | 46 | 47.84 | 48.53 | 46 | 1.84 | 47.84 | 12 | Finishing work | 30.10.2025 |  | 0.69 | Placed at Estimation Folder Annex at Sl No.84_SC
| Kendrapara | Benipur | SC | New Building for Existing SCs | 2022-24 | 46 | 47.55 |  | 46 | 1.55 | 47.55 |  | Lay out given, Contractor not responding, Show cause issued |  | To be dropped
101 | Kendrapada | Kusiapal | SC | New Building for Existing SCs | 2022-24 | 46 | 47.26 | 48.26 | 46 | 1.26 | 47.26 | 28 | Finishing work | 15.10.2024 |  | 1 | Placed at Estimation Folder Annex at Sl No.86_SC
102 | Kendrapada | Manikpur | SC | New Building for Existing SCs | 2022-24 | 46 | 47.57 | 48.41 | 46 | 1.57 | 47.57 |  | completed |  |  | 0.84 | Placed at Estimation Folder Annex at Sl No.87_SC
103 | Kendrapada | Naganpur | SC | New Building for Existing SCs | 2022-24 | 46 | 47.43 | 49.56 | 46 | 1.43 | 47.43 | 35 | completed |  |  | 2.13 | Placed at Estimation Folder Annex at Sl No.82_SC
104 | Kendrapada | Nikirei | SC | New Building for Existing SCs | 2022-24 | 46 | 47.82 | 48.61 | 46 | 1.82 | 47.82 | 33.48 | Completed |  |  | 0.79 | Placed at Estimation Folder Annex at Sl No.83_SC
| Kendrapara | Padanipal | SC | New Building for Existing SCs | 2022-24 | 46 | 48 |  | 46 | 2 | 48 |  | Land dispute. Work to be dropped. |  | To be dropped
105 | Kendrapada | Ranipokhari | SC | New Building for Existing SCs | 2022-24 | 46 | 47.5 | 49.95 | 46 | 1.5 | 47.5 | 28 | Finishing work | 30.10.2025 |  | 2.45 | Placed at Estimation Folder Annex at Sl No.85_SC
| Kendrapara | Srirampur | SC | New Building for Existing SCs | 2022-24 | 46 |  |  | 46 |  | 46 |  | Not started, Contractor not responding |  | To be dropped
106 | Khordha | Amanakuda | SC | New Building for Existing SCs | 2022-24 | 46 |  | 49.99 | 46 |  | 46 | 30.85 | Civil work completed.E.I & Ph work in progress | 30.11.2025 |  | 3.99 | Placed at Estimation Folder Annex at Sl No.91_SC
| Khurda | Basantamala | SC | New Building for Existing SCs | 2022-24 | 46 |  |  | 46 |  | 46 |  | Work not Started |  | To be dropped
107 | Khordha | Bhatakudi | SC | New Building for Existing SCs | 2022-24 | 46 |  | 49.57 | 46 |  | 46 |  | Finishing work in progress | 30.11.2025 |  | 3.57 | Placed at Estimation Folder Annex at Sl No.92_SC
108 | Khordha | Jhinti Sasan | SC | New Building for Existing SCs | 2022-24 | 46 |  | 49.99 | 46 |  | 46 |  | GF Roof cast | 30.12.2025 |  | 3.99 | Placed at Estimation Folder Annex at Sl No.89_SC
109 | Khordha | Kakarudrapur | SC | New Building for Existing SCs | 2022-24 | 46 |  | 49.99 | 46 |  | 46 |  | Roof cast | 31.12.2025 |  | 3.99 | Placed at Estimation Folder Annex at Sl No.89_SC
110 | Khordha | Kalanga | SC | New Building for Existing SCs | 2022-24 | 46 |  | 49.99 | 46 |  | 46 | 12.26 | Finishing work in progress | 30.11.2026 |  | 3.99 | Placed at Estimation Folder Annex at Sl No.94_SC
111 | Khordha | Khalikote | SC | New Building for Existing SCs | 2022-24 | 46 |  | 49.99 | 46 |  | 46 | 12.75 | Finishing work in progress | 30.11.2025 |  | 3.99 | Placed at Estimation Folder Annex at Sl No.95_SC
| Khurda | Sampur | SC | New Building for Existing SCs | 2022-24 | 46 |  |  | 46 |  | 46 |  | Somepur SC is at Finishing stage. |  | To be dropped
112 | Khordha | Sanpadar | SC | New Building for Existing SCs | 2022-24 | 46 |  | 49.99 | 46 |  | 46 | 12.85 | Finishing work in progress | 30.11.2025 |  | 3.99 | Placed at Estimation Folder Annex at Sl No.96_SC
113 | Khordha | Satyabhampur | SC | New Building for Existing SCs | 2022-24 | 46 |  | 49.99 | 46 |  | 46 | 12.82 | Finishing work in progress | 30.10.2025 |  | 3.99 | Placed at Estimation Folder Annex at Sl No.90_SC
114 | Khordha | Sishupalgarh | SC | New Building for Existing SCs | 2022-24 | 46 |  | 49.85 | 46 |  | 46 |  | GF Roof casted | 30.12.2025 |  | 3.85
115 | Khordha | Sompur | SC | New Building for Existing SCs | 2022-24 | 46 |  | 49.99 | 46 |  | 46 | 12.82 | Finishing work in progress | 30.11.2025 |  | 3.99 | Placed at Estimation Folder Annex at Sl No.97_SC
116 | Koraput | Ankula | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 0 | GF Roof Level | 30.11.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.129_SC
117 | Koraput | Aunali | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 9.95 | Finishing work in progress | 30.11.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.116_SC
118 | Koraput | Bada bankidi | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 0 | foundation stage | 30.01.2026 |  | 9 | Placed at Estimation Folder Annex at Sl No.101_SC
119 | Koraput | Badanayakguda | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 0 | foundation work | 30.12.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.114_SC
120 | Koraput | Baragachha | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 0 | EI & PH Work inprogress | 30.10.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.112_SC
121 | Koraput | Bhaluguda | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 0 | Finishing work in progress | 30.11.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.105_SC
122 | Koraput | Bhejaput | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 0 | Completed |  |  | 9 | Placed at Estimation Folder Annex at Sl No.104_SC
123 | Koraput | Bobia | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 0 | FF Brick Work | 30.11.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.130_SC
124 | Koraput | Chandbeda | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 18.4 | completed |  |  | 9 | Placed at Estimation Folder Annex at Sl No.118_SC
125 | Koraput | Dasmantpur | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 17.7 | Completed |  |  | 9 | Placed at Estimation Folder Annex at Sl No.108_SC
126 | Koraput | Deopattangi | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 |  | A/A Done(Tender to be invited) |  |  | 9 | Placed at Estimation Folder Annex at Sl No.103_SC
127 | Koraput | Dunmbaguda | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 0 | FF roof casted | 30.11.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.111_SC
128 | Koraput | Gadapadar | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 0 | GF Lintel Level | 30.11.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.126_SC
129 | Koraput | Girla | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 0 | foundation work | 30.12.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.131_SC
130 | Koraput | Kaligaon | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 |  | Estimate submitted for A/A |  |  | 9 | Placed at Estimation Folder Annex at Sl No.128_SC
131 | Koraput | Kanagam | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 0 | GF Roof level | 30.12.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.119_SC
132 | Koraput | Kanti | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 0 | foundation stage | 46052 |  | 9 | Placed at Estimation Folder Annex at Sl No.98_SC
133 | Koraput | Kathapada | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 0 | Finishing work in progress | 30.10.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.106_SC
134 | Koraput | Kebidi | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 0 | FF Coloumn | 30.12.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.124_SC
135 | Koraput | Kendar | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 0 | Tile work | 30.11.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.115_SC
136 | Koraput | Konga | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 0 | GF Brick Work | 30.12.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.127_SC
137 | Koraput | Kumbhariput | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 0 | foundation stage |  |  | 9 | Placed at Estimation Folder Annex at Sl No.100_SC
138 | Koraput | Kumuli | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 0 | Finishing work in progress | 30.10.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.120_SC
139 | Koraput | Limbaguda | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 22 | Completed |  |  | 9 | Placed at Estimation Folder Annex at Sl No.107_SC
140 | Koraput | Malingjodi | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 11.34 | completed |  |  | 9 | Placed at Estimation Folder Annex at Sl No.113_SC
141 | Koraput | Mujanga | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 0 | EI & PH Work inprogress | 30.10.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.110_SC
142 | Koraput | Munja | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 0 | GF Brick work | 30.12.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.121_SC
143 | Koraput | Nuagaon | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 0 | Finishing work in progress | 30.10.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.123_SC
144 | Koraput | Parjakubadi | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 0 | Completed |  |  | 9 | Placed at Estimation Folder Annex at Sl No.99_SC
145 | Koraput | Rgirliguma | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 0 | Plaster work in progress | 30.11.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.109_SC
146 | Koraput | Sanaparia | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 0 | FF roof level | 30.12.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.117_SC
147 | Koraput | Sekram | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 0 | FF roof casted | 30.11.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.102_SC
148 | Koraput | Semalaguda | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 21.89 | Completed |  |  | 9 | Placed at Estimation Folder Annex at Sl No.122_SC
149 | Koraput | Umuri | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 |  | A/A Done(Tender to be invited) |  |  | 9 | Placed at Estimation Folder Annex at Sl No.125_SC
150 | Mayurbhanj | Agual | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 40 | Completed & Handed over |  |  | 4
151 | Mayurbhanj | Ambadali | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 25 | Finishing work in progress | 30.10.2025 |  | 4
152 | Mayurbhanj | B Kata | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 27.53 | Finishing work in progress | 30.10.2025 |  | 4
153 | Mayurbhanj | Badbantha | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 32 | Civil & EI work completed , PH in progress | 30.10.2025 |  | 3
154 | Mayurbhanj | Baddeuli | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 40.53 | Completed & Handed over |  |  | 3
155 | Mayurbhanj | Badkasira | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 48.44 | Completed & Handed over |  |  | 3
156 | Mayurbhanj | Baiganbadia | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 21.1 | Civil Completed , EI & PH in progress | 30.10.2025 |  | 4
157 | Mayurbhanj | Bala | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 42.26 | Completed & Handed over |  |  | 3
158 | Mayurbhanj | Bangra | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 22 | Finishing work in progress | 30.10.2025 |  | 4
159 | Mayurbhanj | Bankati | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 30.37 | Civil & EI work completed , PH in progress | 30.10.2025 |  | 3
160 | Mayurbhanj | Barajiani | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 27.05 | Completed |  |  | 3
161 | Mayurbhanj | Basantapur | SC | New Building for Existing SCs | 2022-24 | 46 | 50 | 60.49 | 46 |  | 46 |  | Agreement done, workto be started |  |  | 14.49
162 | Mayurbhanj | Batpalsa | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 20.19 | Completed & Handed over |  |  | 3
163 | Mayurbhanj | Baunsnali | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 38.44 | Completed & Handed over |  |  | 3
164 | Mayurbhanj | Bautibeda | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 40.53 | Completed & Handed over |  |  | 3
165 | Mayurbhanj | Beldiha | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 18.44 | Finishing work in progress | 30.10.2025 |  | 4
166 | Mayurbhanj | Bhalkichua | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 24.09 | Completed |  |  | 3
167 | Mayurbhanj | Bhandan | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 48.44 | Completed & Handed over |  |  | 3
168 | Mayurbhanj | Bhimda | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 50 | Completed & Handed over |  |  | 4
169 | Mayurbhanj | Bhuasuni | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 27.68 | Finishing work in progress | 30.10.2025 |  | 3
170 | Mayurbhanj | Budhikhamari | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 |  | Tender to be invited |  |  | 3
171 | Mayurbhanj | Chadheibhol | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 40.53 | Completed & Handed over |  |  | 3
172 | Kendujhar | Chandabila | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 23 | Finishing work in progress | 30.10.2025 |  | 4
173 | Mayurbhanj | Chandanpur | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 27.49 | Completed & Handed over |  |  | 3
174 | Mayurbhanj | Chelia B | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 50 | Completed & Handed over |  |  | 4
175 | Mayurbhanj | Chheligoduli | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 38.44 | Completed & Handed over |  |  | 3
176 | Mayurbhanj | Chuhat | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 37.5 | Completed |  |  | 4
177 | Mayurbhanj | Dahikuti | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 25 | Civil completed, EI & PH work in progress | 30.10.2025 |  | 4
178 | Mayurbhanj | Demphauda | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 50 | Completed & Handed over |  |  | 4
179 | Mayurbhanj | Deokundi | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 16 | Completed |  |  | 3
180 | Mayurbhanj | Dewanbahali | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 12.25 | Completed & Handed over |  |  | 4
181 | Mayurbhanj | Dhalabani | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 48.44 | Completed & Handed over |  |  | 3
182 | Mayurbhanj | Dhanputa | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 31.48 | Finishing work in progress | 30.10.2025 |  | 4
183 | Mayurbhanj | Dhobanisole | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 36.1 | Civil Completed , EI & PH in progress | 30.10.2025 |  | 3
184 | Mayurbhanj | Digarastia | SC | New Building for Existing SCs | 2022-24 | 46 | 50 | 60.49 | 46 |  | 46 |  | Site selection done, estimate prepared |  |  | 14.49 | Placed at Estimation Folder Annex at Sl No. 67_SC NS
185 | Mayurbhanj | Dudhiani | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 36.84 | Civil completed, EI & PH work in progress | 30.11.2025 |  | 3
186 | Mayurbhanj | Dudhiasole | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 21.05 | Civil Completed , EI & PH in progress | 30.10.2025 |  | 4
187 | Mayurbhanj | Durgapur | SC | New Building for Existing SCs of Badasahi Block | 2022-24 | 46 | 50 |  | 46 |  | 46 | 30.37 | Completed |  |  | 4
188 | Mayurbhanj | Durgapur | SC | New Building for Existing SCs of Betanati Block | 2022-24 | 46 | 50 |  | 46 |  | 46 | 14.5 | Finishing work in progress | 30.10.2025 |  | 4
189 | Mayurbhanj | Ektali | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 29.05 | Finishing work in progress | 30.10.2025 |  | 3
190 | Mayurbhanj | Gaddaulia | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 30 | Completed & Handed over |  |  | 4
191 | Mayurbhanj | Gadsimilipal | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 48.44 | Completed & Handed over |  |  | 3
192 | Mayurbhanj | Ghatkuanri | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 25 | Civil Completed , EI & PH not started | 30.10.2025 |  | 3
193 | Mayurbhanj | Golagadia | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 20.15 | Finishing work in progress | 30.10.2025 |  | 4
194 | Mayurbhanj | Gopinathpur | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 22.51 | Completed |  |  | 3
195 | Mayurbhanj | Gourachandrapur | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 12 | Finishing work in progress | 30.10.2025 |  | 4
196 | Mayurbhanj | Gudialbandh | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 50 | Completed & Handed over |  |  | 4
197 | Mayurbhanj | Haripur | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 23 | Finishing work in progress | 30.10.2025 |  | 4
198 | Mayurbhanj | Jadida | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 27 | Finishing work in progress | 30.10.2025 |  | 4
199 | Mayurbhanj | Jadunathpur | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 44 | Completed & Handed over |  |  | 4
200 | Mayurbhanj | Jaypur | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 38.8 | Completed & Handed over |  |  | 3
201 | Mayurbhanj | Kailashchandrapur | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 |  | Ground floor roof level | 30.12.2025 |  | 4
202 | Mayurbhanj | Kainfulia | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 49.5 | Completed & Handed over |  |  | 4
203 | Mayurbhanj | Kalabadia | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 36.68 | Completed & Handed over |  |  | 3
204 | Mayurbhanj | Kamarpal | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 21 | Finishing work in progress | 30.10.2025 |  | 4
205 | Mayurbhanj | Karanjia | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 34 | Completed & Handed over |  |  | 4
206 | Mayurbhanj | Kasiabeda | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 38.8 | Completed & Handed over |  |  | 3
207 | Mayurbhanj | Kathabaria | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 48.44 | Completed & Handed over |  |  | 3
208 | Mayurbhanj | Kathsirshi | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 21 | Civil completed, EI & PH work in progress | 30.10.2025 |  | 4
209 | Mayurbhanj | Khanta | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 30 | Civil work completed , EI & PH in progress | 30.10.2025 |  | 3
210 | Mayurbhanj | Khanua | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 50 | Completed & Handed over |  |  | 4
211 | Mayurbhanj | KM Kota | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 20.36 | Civil work completed , EI & PH in progress | 30.10.2025 |  | 3
212 | Mayurbhanj | Kochilakhunta | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 50 | Completed & Handed over |  |  | 4
213 | Mayurbhanj | Kuabuda | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 21.12 | Civil completed, EI & PH work in progress | 30.10.2025 |  | 4
214 | Mayurbhanj | Kuliposi | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 40.81 | Completed & Handed over |  |  | 3
215 | Mayurbhanj | Kurulia | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 30 | Completed & Handed over |  |  | 3
216 | Mayurbhanj | Kusumi | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 38 | civil work completed, EI & PH in progress | 30.10.2025 |  | 3
217 | Mayurbhanj | Laxmiposi | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 32.51 | civil work completed, EI & PH in progress | 30.10.2025 |  | 4
218 | Mayurbhanj | Mahubhandar | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 40.53 | Completed & Handed over |  |  | 3
219 | Mayurbhanj | Majhigaon | SC | New Building for Existing SCs | 2022-24 | 46 | 49 | 65 | 46 |  | 46 |  | Site selection done |  |  | 19 | Placed at Estimation Folder Annex at Sl No. 65_SC NS
220 | Mayurbhanj | Manada | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 48.44 | Completed & Handed over |  |  | 3
221 | Mayurbhanj | Matiagarh | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 18.5 | Finishing work in progress | 30.10.2025 |  | 3
222 | Mayurbhanj | Mundathakura | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 22.95 | Civil work completed , EI & PH in progress | 30.10.2025 |  | 3
223 | Mayurbhanj | Nischinta | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 13.2 | Finishing work in progress | 30.10.2025 |  | 3
224 | Mayurbhanj | Nitei | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 38.28 | Completed & Handed over |  |  | 3
225 | Mayurbhanj | Parulia | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 21 | Civil completed, EI & PH work in progress | 30.10.2025 |  | 4
226 | Mayurbhanj | Pathuri | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 21.81 | Civil work completed , EI & PH in progress | 30.10.2025 |  | 3
227 | Mayurbhanj | Podagarh | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 48.44 | Completed & Handed over |  |  | 3
228 | Mayurbhanj | Pratappur | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 25 | Completed & Handed over |  |  | 4
229 | Mayurbhanj | Pundida | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 40.53 | Completed & Handed over |  |  | 3
230 | Mayurbhanj | Raipal | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 22.32 | Completed & Handed over |  |  | 4
231 | Mayurbhanj | Rodhang | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 44.69 | Completed & Handed over |  |  | 3
232 | Mayurbhanj | Sandundu | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 32.89 | Civil work completed , EI & PH in progrss | 30.10.2025 |  | 3
233 | Mayurbhanj | Sangan | SC | New Building for Existing SCs | 2022-24 | 46 | 49 |  | 46 |  | 46 | 39.11 | Completed & Handed over |  |  | 3
234 | Mayurbhanj | Sanpurunapani | SC | New Building for Existing SCs | 2022-24 | 46 | 49 | 65 | 46 |  | 46 |  | Site selection done |  |  | 19 | Placed at Estimation Folder Annex at Sl No. 66_SC NS
235 | Mayurbhanj | Sialighaty | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 50 | Completed & Handed over |  |  | 4
236 | Mayurbhanj | Singatia | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 25.2 | Completed |  |  | 4
237 | Mayurbhanj | Sukhilahar | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 25 | Finishing work in progress | 30.10.2025 |  | 4
238 | Mayurbhanj | Takatpur | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 22 | Finishing work in progress | 30.10.2025 |  | 4
239 | Mayurbhanj | Tentuligaon | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 26.36 | Completed & Handed over |  |  | 4
240 | Mayurbhanj | Ufalgadia | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 10.5 | Ground floor roof casted | 30.10.2025 |  | 4
241 | Mayurbhanj | Uthaninuagaon | SC | New Building for Existing SCs | 2022-24 | 46 | 50 |  | 46 |  | 46 | 28 | Civil completed, EI & PH work in progress | 30.10.2025 |  | 4
242 | Nabarangpur | Bada Olma | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 |  | foundation | 30.10.2025 |  | 9
243 | Nayagada | Barakoli | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 15.66 | EI Work inprogress | 30.10.2025 |  | 9
244 | Nayagada | Bodasa | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 26.6 | Completed |  |  | 9
245 | Nayagada | Haripur- | SC | New Building for Existing SCs | 2022-24 | 46 |  | 50.6 | 46 |  | 46 | 13.8 | Completed |  |  | 4.6
246 | Nayagada | Kishoreprasad | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 |  | AA done tender to be invited |  |  | 9
247 | Nayagada | Machhipada | SC | New Building for Existing SCs | 2022-24 | 46 |  | 50.6 | 46 |  | 46 | 45.54 | Completed |  |  | 4.6
248 | Nayagada | Natugaon | SC | New Building for Existing SCs | 2022-24 | 46 |  | 50.6 | 46 |  | 46 | 13.8 | Completed |  |  | 4.6
249 | Nayagada | Panusahipatna | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 15.37 | EI Work inprogress | 30.10.2025 |  | 9
250 | Nayagada | Surukabadi | SC | New Building for Existing SCs | 2022-24 | 46 |  | 50.6 | 46 |  | 46 | 20.25 | Completed |  |  | 4.6
251 | Puri | Alasahi | SC | New Building for Existing SCs | 2022-24 | 46 | 46.5 |  | 46 |  | 46 |  | Site selection under process |  |  | 0.5
252 | Puri | Analjodi | SC | New Building for Existing SCs | 2022-24 | 46 | 47.5 |  | 46 |  | 46 | 47.5 | Completed & Handed over |  |  | 1.5
253 | Puri | Ansala | SC | New Building for Existing SCs | 2022-24 | 46 | 47.5 |  | 46 |  | 46 | 25.6 | 1st floor colum casting |  |  | 1.5
| Puri | Badal | SC | New Building for Existing SCs | 2022-24 | 46 |  |  | 46 |  | 46 |  | No such SC available in NHM PIP |  | To be dropped
254 | Puri | Balabhadrapur | SC | New Building for Existing SCs | 2022-24 | 46 | 47 | 47.5 | 46 |  | 46 |  | Plinth Level |  |  | 1.5
255 | Puri | Bangurigaon | SC | New Building for Existing SCs | 2022-24 | 46 | 47.5 |  | 46 |  | 46 | 25.6 | Finishing works in progress | 30.10.25 |  | 1.5
256 | Puri | Barakera | SC | New Building for Existing SCs | 2022-24 | 46 | 46.51 |  | 46 |  | 46 | 7.5 | 1st floor work in progress | 30.10.25 |  | 0.51
257 | Puri | Bindhana | SC | New Building for Existing SCs | 2022-24 | 46 | 47.5 |  | 46 |  | 46 | 30 | Finishing works in progress | 30.10.25 |  | 1.5
258 | Puri | Chitraswari | SC | New Building for Existing SCs | 2022-24 | 46 | 47.5 |  | 46 |  | 46 | 23.5 | Civil works completed and EI and PH in progress. | 30.10.25 |  | 1.5
259 | Puri | Dhanakera | SC | New Building for Existing SCs | 2022-24 | 46 | 47.5 |  | 46 |  | 46 |  | Completed out of State budget |  |  | 1.5
260 | Puri | Edvans | SC | New Building for Existing SCs | 2022-24 | 46 | 46.5 |  | 46 |  | 46 | 10 | 1st floor Roof level | 30.10.25 |  | 0.5
261 | Puri | Gadamurgasira | SC | New Building for Existing SCs | 2022-24 | 46 | 46.82 |  | 46 |  | 46 |  | Buildingless SC |  |  | 0.82
262 | Puri | Gambharipada | SC | New Building for Existing SCs | 2022-24 | 46 | 47.5 |  | 46 |  | 46 | 38.16 | Completed & Handed over |  |  | 1.5
263 | Puri | Jaunli Pokhari | SC | New Building for Existing SCs | 2022-24 | 46 | 47.5 |  | 46 |  | 46 | 32.69 | Completed & Handed over |  |  | 1.5
264 | Puri | Kanpur | SC | New Building for Existing SCs | 2022-24 | 46 | 46.76 |  | 46 |  | 46 | 27.5 | Finishing works in progress | 30.10.25 |  | 0.76
| Puri | Kunjar | SC | New Building for Existing SCs | 2022-24 | 46 |  |  | 46 |  | 46 |  | Land dispute |  | To be dropped
265 | Puri | Malud | SC | New Building for Existing SCs | 2022-24 | 46 | 47.5 |  | 46 |  | 46 | 29.78 | Completed & Handed over |  |  | 1.5
266 | Puri | Motari | SC | New Building for Existing SCs | 2022-24 | 46 | 46.92 |  | 46 |  | 46 | 20 | Civil works completed and EI and PH in progress. | 30.10.25 |  | 0.92
| Puri | Nadakhanda | SC | New Building for Existing SCs | 2022-24 | 46 |  |  | 46 |  | 46 |  | Land not available |  | To be dropped
267 | Puri | Nuagaon. | SC | New Building for Existing SCs | 2022-24 | 46 | 46.51 |  | 46 |  | 46 | 46.51 | Completed & Handed over |  |  | 0.51
268 | Puri | Olardi | SC | New Building for Existing SCs | 2022-24 | 46 | 47.5 |  | 46 |  | 46 |  | Site selection under process |  |  | 1.5
269 | Puri | Rua | SC | New Building for Existing SCs | 2022-24 | 46 | 47.8 |  | 46 |  | 46 | 43.94 | Completed & Handed over |  |  | 1.8
270 | Puri | Satarash | SC | New Building for Existing SCs | 2022-24 | 46 | 47.5 |  | 46 |  | 46 | 30.72 | Finishing works in progress | 30.10.25 |  | 1.5
271 | Puri | Sauria | SC | New Building for Existing SCs | 2022-24 | 46 | 46.48 |  | 46 |  | 46 | 20 | Finishing works in progress | 30.10.25 |  | 0.48
| Puri | simili | SC | New Building for Existing SCs | 2022-24 | 46 |  |  | 46 |  | 46 |  | Land not available |  | To be dropped
272 | Puri | Siso | SC | New Building for Existing SCs | 2022-24 | 46 | 47.5 |  | 46 |  | 46 | 47.5 | Completed & Handed over |  |  | 1.5
273 | Puri | Telengapada | SC | New Building for Existing SCs | 2022-24 | 46 | 47.5 |  | 46 |  | 46 | 47.5 | Completed & Handed over |  |  | 1.5
| Puri | Trilochanpur | SC | New Building for Existing SCs | 2022-24 | 46 |  |  | 46 |  | 46 |  | Land not available |  | To be dropped
274 | Rayagada | Agula | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 4 | foundation stage | 25.05.2026 |  | 9 | Placed at Estimation Folder Annex at Sl No.177_SC
275 | Rayagada | Bairagi Halwa | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 8.21 | work completed handed over but external electrification required |  |  | 9
276 | Rayagada | Bhairabagada | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 6 | finishing stage | 31.10.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.178_SC
277 | Rayagada | Chalkamba | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 9 | EI & PH work in progress | 30.11.2025 |  | 9
278 | Rayagada | D Korala | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 8 | 1st floor. Work in progress | 31.10.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.174_SC
279 | Rayagada | Dunduli | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 13 | finishing stage | 31.10.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.175_SC
280 | Rayagada | Hanumantpur | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 24 | work completed handed over but external electrification required |  |  | 9
281 | Rayagada | Indupur | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 9 | work completed handed over but external electrification required |  |  | 9
282 | Rayagada | Jarapa | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 24 | work completed handed over but external electrification required |  |  | 9
283 | Rayagada | Jhigidi | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 14.871 | 1st floor work in progress | 31.10.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.172_SC
284 | Rayagada | Jhorodi | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 16.5 | Slab casted ,1st floor work in progress | 31.12.2025 |  | 9
285 | Rayagada | Kailashpur | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 9 | finishing stage | 31.10.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.176_SC
286 | Rayagada | Karubai | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 36 | finishing stage | 31.10.2025 |  | 9
| Rayagada | Khedapada | SC | New Building for Existing SCs | 2022-24 | 46 |  |  | 46 |  | 46 |  |  |  | To be dropped
287 | Rayagada | Korapa | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 10 | finishing stage | 31.10.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.173_SC
288 | Rayagada | Omidingi | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 4 | finishing stage | 25.11.2025 |  | 9
289 | Rayagada | Penta | SC | New Building for Existing SCs | 2022-24 | 46 |  | 55 | 46 |  | 46 | 14.844 | 1st floor brick work in progress | 30.11.2025 |  | 9 | Placed at Estimation Folder Annex at Sl No.179_SC
| Rayagada | Sankarada | SC | New Building for Existing SCs | 2022-24 | 46 |  |  | 46 |  | 46 |  |  |  | To be dropped
290 | Sambalpur | Sindurpank | SC | New Building for Existing SCs | 2022-24 | 46 |  | 50.6 | 46 |  | 46 | 0 | Layout Given |  |  | 4.6 | Placed at Estimation Folder Annex at Sl No.180_SC
|  |  | Grand Total |  |  | 13340 | 7083.26 | 8133.9571 | 13340 | 9.42 | 13349.42 | 6761.6725 |  |  |  | 1867.7971
[7 empty] | 7248.26 |  |  |  | 13487.42
2078.93
Sonpur

## Annex-7-SC 2024-26
Civil Annexure (for New Works-SC) - 2024-26, Odisha
Sl. No. | Name of the District | Name of the Block | Name of the Facility | Type of the Facility | If existing Premises, then Land Details (In Sqft) |  |  |  | In Case of New Sites |  |  | Total Project Cost (in Rs. Lakhs) | Total Approved Amount till 2024-26 | Revised Project Cost (in Rs. Lakhs) | Fund Approved in 2026-27 (Rs. In Lakhs) | Physical Status of the Work
[5 empty] | Total Land Area | Total Built-up Area | Clear Open Space Available | Addl. Area if any can be created through demolition of existing building | Land Area available in Sqft. | Distance from existing Site | Land in the name of H&FW Deptt. (Yes/ No)
1 | Anugola | R.K.Nagar | Badagovindapur | SC | 3600 | 1000 | 2600 |  |  |  |  | 55 | 55 | 65 | 10
2 | Anugola | Kaniha | Badagunduri | SC | 3177 | 1000 | 2177 |  |  |  |  | 55 | 55 | 65 | 10
3 | Anugola | Banarpal | Badakerjang | SC | 32227 | 2500 | 29727 |  |  |  |  | 55 | 55 | 65 | 10
| Angul | Kaniha | Bajrakote | SC |  |  |  |  | No |  |  | 55 | 55 |  |  | Land not finanlised | To be dropped
4 | Anugola | Talcher | Dharampur | SC | 6500 | 1500 | 5000 |  |  |  |  | 55 | 55 | 65 | 10
5 | Anugola | Athamallik | Kaintragarh | SC |  |  |  |  | 3600 | 3 | No | 55 | 55 | 65 | 10 | Land identified but land schedule not submitted by Revenue department.
| Angul | R.K.Nagar | Persumal | SC |  |  |  |  | No |  |  | 55 | 55 |  |  | Land not identified | To be dropped
6 | Anugola | Anugola | Shradhapur B | SC |  |  |  |  | 5000 | 2 | No | 55 | 55 | 65 | 10 | Land identified but land schedule not submitted by Revenue department.
7 | Anugola | Athamallik | Thakurhgarh | SC |  |  |  |  | 3800 | 2.5 | No | 55 | 55 | 65 | 10 | Land identified but land schedule not submitted by Revenue department.
8 | Balangir | Deogaon | Arjunpur | SC |  |  |  |  | 4360 | 1KM | Yes | 55 | 55 | 60.3 | 5.3 | Agreement to be drawn
9 | Balangir | Turekela | Badbanki | SC |  |  |  |  | 8720 | 1KM | Yes | 55 | 55 | 60.22 | 5.22 | Agreement to be drawn
10 | Balangir | Khaprakhol | Bagmunda | SC |  |  |  |  | 4360 | 1KM | Yes | 55 | 55 | 60.1 | 5.1 | Agreement to be drawn
11 | Balangir | Deogaon | Bandhpara | SC |  |  |  |  | 4360 | 2KM | Yes | 55 | 55 | 60.39 | 5.39 | Agreement to be drawn
12 | Balangir | Titilagarh | Banjipadar | SC |  |  |  |  | 4360 | 2KM | Yes | 55 | 55 | 60.01 | 5.01 | Agreement to be drawn
13 | Balangir | Loisingha | Budhipadar | SC | 10000 | 1200 | 8800 | No |  |  | Yes | 55 | 55 | 60.06 | 5.06 | Agreement to be drawn
14 | Balangir | Muribahal | Chalki | SC |  |  |  |  | 4360 | 0.50KM | Yes | 55 | 55 | 60.05 | 5.05 | Agreement to be drawn
15 | Balangir | Bangomunda | Chandotora | SC |  |  |  |  | 8720 | 50Mtr | Yes | 55 | 55 | 59.91 | 4.91 | Agreement to be drawn
16 | Balangir | Turekela | Chaulsukha | SC |  |  |  |  | 8720 | 0.50KM | Yes | 55 | 55 | 60.22 | 5.22 | Agreement to be drawn
17 | Balangir | Patnagarh | Gangasagar | SC |  |  |  |  | 4360 | 1.5KM | Yes | 55 | 55 | 60.1 | 5.1 | Agreement to be drawn
18 | Balangir | Patnagarh | Jhankarpali | SC |  |  |  |  | 4360 | 2KM | Yes | 55 | 55 | 60.1 | 5.1 | Agreement to be drawn
19 | Balangir | Bangomunda | Jharial | SC |  |  |  |  | 8720 | 50Mtr | Yes | 55 | 55 | 60.17 | 5.17 | Agreement to be drawn
20 | Balangir | Turekela | Jharni | SC |  |  |  |  | 8720 | 0.50KM | Yes | 55 | 55 | 60.24 | 5.24 | Agreement to be drawn
21 | Balangir | Saintala | Kandhkelgaon | SC |  |  |  |  | 4360 | 1KM | Yes | 55 | 55 | 60.1 | 5.1 | Agreement to be drawn
22 | Balangir | Belpada | Kanut | SC |  |  |  |  | 4360 | 1KM | Yes | 55 | 55 | 60.1 | 5.1 | Agreement to be drawn
23 | Balangir | Saintala | Karamtala | SC |  |  |  |  | 4360 | 2KM | Yes | 55 | 55 | 60.1 | 5.1 | Agreement to be drawn
24 | Balangir | Bangomunda | Khaira | SC |  |  |  |  | 6540 | 1KM | Yes | 55 | 55 | 60.17 | 5.17 | Agreement to be drawn
25 | Balangir | Khaprakhol | Sauntpur | SC |  |  |  |  | 4360 | 1 KM | Yes | 55 | 55 | 60.26 | 5.26 | Agreement to be drawn ( Diverted from Khaprakhol SC) Letter No- OSH&FWS/4357, Dt-22-04-2025
26 | Balangir | Titilagarh | Kursud | SC |  |  |  |  | 4360 | 2.5KM | Yes | 55 | 55 | 60.25 | 5.25 | Agreement to be drawn
| Balasore | Bhogarai | Alalbindha | SC | No land | [6 empty] | 55 | 55 |  |  | No land | To be dropped
27 | Baleshwar | Baliapal | Asti | SC |  |  |  |  | 5350 | 2 | N | 55 | 55 | 62.5 | 7.5 | Tender will be invited
28 | Baleshwar | Jaleswar | Baradiha | SC |  |  |  |  | 5350 | 2.5 | N | 55 | 55 | 62.5 | 7.5 | Tender will be invited
29 | Baleshwar | Jaleswar | Bartana | SC | 4000 | 2200 | 800 |  |  |  |  | 55 | 55 | 62.5 | 7.5 | Tender will be invited
30 | Baleshwar | Remuna | Bhuinpada | SC | 2145 | 1148 | 977 |  |  |  |  | 55 | 55 | 60.42 | 5.42 | Agreement stage
31 | Baleshwar | Baliapal | Chaumukh | SC |  |  |  |  | 3200 | 2.5 | N | 55 | 55 | 62.5 | 7.5 | Tender will be invited
32 | Baleshwar | Bhogarai | Dehurda | SC |  |  |  |  | 5350 | Adjacent | N | 55 | 55 | 62.5 | 7.5 | Tender will be invited
33 | Baleshwar | Remuna | Durgadevi | SC | 2145 | 1148 | 977 |  |  |  |  | 55 | 55 | 59.46 | 4.46 | agreement stage
34 | Baleshwar | Bhogarai | Fulbani | SC |  |  |  |  | 5350 | Adjacent | N | 55 | 55 | 62.5 | 7.5 | Tender will be invited
35 | Baleshwar | Bhogarai | Kalehi | SC |  |  |  |  | 4800 | 0.5 | N | 55 | 55 | 62.5 | 7.5 | Tender will be invited
| Balasore | Simulia | Khirkona | SC | No land | [6 empty] | 55 | 55 |  |  |  | To be dropped
36 | Baleshwar | Bhogarai | Kusuda | SC |  |  |  |  | 5350 | Adjacent | N | 55 | 55 | 62.5 | 7.5 | Tender will be invited
37 | Baleshwar | Remuna | Makanda | SC | 2145 | 1148 | 977 |  |  |  |  | 55 | 55 | 60.23 | 5.23 | agreement stage
38 | Baleshwar | Soro | Mangalpur | SC | 6000 | 1148 | 1148 | No |  |  |  | 55 | 55 | 60.42 | 5.42 | Greement drawn
| Balasore | Bhogarai | Mohagab | SC |  |  |  |  | NO land available |  |  | 55 | 55 |  |  | As no land Availabe, Hence dropped | To be dropped
39 | Baleshwar | Bhogarai | Nahara | SC |  |  |  |  | 4300 | 0.8 | N | 55 | 55 | 62.5 | 7.5 | Tender will be invited
40 | Baleshwar | Bhogarai | Putina | SC |  |  |  |  | 4300 | 0.5 | N | 55 | 55 | 62.5 | 7.5 | Tender will be invited
41 | Baleshwar | Bhogarai | Rankotha | SC |  |  |  |  | 4300 | Adjacent | N | 55 | 55 | 62.5 | 7.5 | Tender will be invited
42 | Baleshwar | Baliapal | Ratai | SC |  |  |  |  | 3700 | 0.3 | N | 55 | 55 | 62.5 | 7.5 | Tender will be invited
| Baragarh | Ambabhona | Ambabhona | SC |  |  |  |  | No | No | No | 55 | 55 |  |  | These all are PHC Headquarter Sc.New Space requires with in 2-3 km radius.Till now land not finalized. | To be dropped
| Baragarh | Ambabhona | Dunguri | SC |  |  |  |  | No | No | No | 55 | 55 |  |  | These all are PHC Headquarter Sc.New Space requires with in 2-3 km radius.Till now land not finalized. | To be dropped
| Baragarh | Bheden | Gandturum | SC |  |  |  |  | No | No | No | 55 | 55 |  |  | These all are PHC Headquarter Sc.New Space requires with in 2-3 km radius.Till now land not finalized. | To be dropped
| Baragarh | Padampur | Ghanamal | SC |  |  |  |  | No | No | No | 55 | 55 |  |  | These all are PHC Headquarter Sc.New Space requires with in 2-3 km radius.Till now land not finalized. | To be dropped
| Baragarh | Attabira | Janhapada | SC |  |  |  |  | No | No | No | 55 | 55 |  |  | These all are PHC Headquarter Sc.New Space requires with in 2-3 km radius.Till now land not finalized. | To be dropped
| Baragarh | Paikmal | Jhitiki | SC |  |  |  |  | No | No | No | 55 | 55 |  |  | These all are PHC Headquarter Sc.New Space requires with in 2-3 km radius.Till now land not finalized. | To be dropped
| Baragarh | Attabira | Kadobahal | SC |  |  |  |  | No | No | No | 55 | 55 |  |  | These all are PHC Headquarter Sc.New Space requires with in 2-3 km radius.Till now land not finalized. | To be dropped
| Baragarh | Bhatli | Kamgaon | SC |  |  |  |  | No | No | No | 55 | 55 |  |  | These all are PHC Headquarter Sc.New Space requires with in 2-3 km radius.Till now land not finalized. | To be dropped
| Baragarh | Bijepur | Kharmunda | SC |  |  |  |  | No | No | No | 55 | 55 |  |  | These all are PHC Headquarter Sc.New Space requires with in 2-3 km radius.Till now land not finalized. | To be dropped
| Baragarh | Bargarh | Khuntpali | SC |  |  |  |  | No | No | No | 55 | 55 |  |  | These all are PHC Headquarter Sc.New Space requires with in 2-3 km radius.Till now land not finalized. | To be dropped
| Baragarh | Barpali | Kumbhari | SC |  |  |  |  | No | No | No | 55 | 55 |  |  | These all are PHC Headquarter Sc.New Space requires with in 2-3 km radius.Till now land not finalized. | To be dropped
| Baragarh | Ambabhona | Lakhanpur | SC |  |  |  |  | No | No | No | 55 | 55 |  |  | These all are PHC Headquarter Sc.New Space requires with in 2-3 km radius.Till now land not finalized. | To be dropped
| Baragarh | Attabira | Larambha | SC |  |  |  |  | No | No | No | 55 | 55 |  |  | These all are PHC Headquarter Sc.New Space requires with in 2-3 km radius.Till now land not finalized. | To be dropped
| Baragarh | Jharbandh | Laudiidhara | SC |  |  |  |  | No | No | No | 55 | 55 |  |  | These all are PHC Headquarter Sc.New Space requires with in 2-3 km radius.Till now land not finalized. | To be dropped
| Baragarh | Padampur | Luharpalii | SC |  |  |  |  | No | No | No | 55 | 55 |  |  | These all are PHC Headquarter Sc.New Space requires with in 2-3 km radius.Till now land not finalized. | To be dropped
| Baragarh | Attabira | Paharsirgida | SC |  |  |  |  | No | No | No | 55 | 55 |  |  | These all are PHC Headquarter Sc.New Space requires with in 2-3 km radius.Till now land not finalized. | To be dropped
| Baragarh | Sohela | Panimora | SC |  |  |  |  | No | No | No | 55 | 55 |  |  | These all are PHC Headquarter Sc.New Space requires with in 2-3 km radius.Till now land not finalized. | To be dropped
| Baragarh | Bheden | Remunda | SC |  |  |  |  | No | No | No | 55 | 55 |  |  | These all are PHC Headquarter Sc.New Space requires with in 2-3 km radius.Till now land not finalized. | To be dropped
| Bhadrak | Bhandaripokhari | Akhuapada | SC |  |  |  |  | no |  |  | 55 | 55 |  |  | Site not finalized | To be dropped
| Boudh | Harbhanga | Adenigarh | SC |  |  |  |  | NA |  |  | 55 | 55 |  |  | Site not finalised | To be dropped
| Boudh | Boudh | Badhigaon | SC |  |  |  |  | NA |  |  | 55 | 55 |  |  | Site not finalised | To be dropped
| Boudh | Kantamal | Bargochha | SC |  |  |  |  | NA |  |  | 55 | 55 |  |  | Site not finalised | To be dropped
43 | Boudh | Harbhanga | Charichak | SC | 12 dC | 1000 SFT | Yes | Yes |  |  |  | 55 | 55 | 65 | 10 | Demolition of old building
44 | Boudh | Boudh | Gochhapada | SC | 12 Dc | 1000 sft | Yes | Yes |  |  |  | 55 | 55 | 65 | 10 | Demolition of old building
45 | Boudh | Harbhanga | Harbhanga | SC | 12 Dc | 1000 sft | No | NA |  |  |  | 55 | 55 | 65 | 10 | Demolition of old building
46 | Boudh | Kantamal | Kantamal | SC | 12 Dc | 1000 sft | No | NA |  |  |  | 55 | 55 | 65 | 10 | Demolition of old building
| Boudh | Boudh | Rugudikanpa | SC |  |  |  |  | NA |  |  | 55 | 55 |  |  | Site not finalised | To be dropped
47 | Boudh | Boudh | Tilpanga | SC | 15 Dc | 1000 sft | No | NA |  |  |  | 55 | 55 | 65 | 10
48 | Kataka | Tigiria | Bindhanima | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 65 | 10 | File put up for A/A
49 | Kataka | Narasinghpur | Ekdal | SC | 3000 | 1100 | 1500 | No | 0 | 0 | 0 | 55 | 55 | 65 | 10 | File put up for A/A
50 | Kataka | Baramba | Gopinathpur | SC | 3000 | 1100 | 1500 | No | 0 | 0 | 0 | 55 | 55 | 65 | 10 | File put up for A/A
51 | Kataka | Badamba | Jhajia | SC | 3000 | 1100 | 1500 | No | 0 | 0 | 0 | 55 | 55 | 65 | 10 | File put up for A/A
52 | Kataka | Badamba | Maniabandha | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 65 | 10 | File put up for A/A
53 | Kataka | Narasinghpur | Narsinghpur | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 65 | 10 | File put up for A/A
54 | Debagada | Tileibani | Badchhapal | SC | 7500 |  | 2500 |  |  |  |  | 55 | 55 | 65 | 10 | Estimate under preparation
55 | Debagada | Barkote | Barkote | SC | [6 empty] | No | 55 | 55 | 65 | 10 | Estimate under preparation
56 | Debagada | Barkote | Basalai | SC | [6 empty] | No | 55 | 55 | 65 | 10 | Estimate under preparation
57 | Debagada | Reamal | Chadheimara | SC | 7500 |  | 2500 |  |  |  |  | 55 | 55 | 65 | 10 | Estimate under preparation
58 | Debagada | Reamal | Chhatabar | SC | [6 empty] | No | 55 | 55 | 65 | 10 | Estimate under preparation
59 | Debagada | Tileibani | Dimrikuda | SC | [6 empty] | No | 55 | 55 | 65 | 10 | Estimate under preparation
60 | Debagada | Barkote | Kaliaapal | SC | [6 empty] | No | 55 | 55 | 65 | 10 | Estimate under preparation
61 | Debagada | Tileibani | Kendeijuri | SC | [6 empty] | No | 55 | 55 | 65 | 10 | Estimate under preparation
62 | Debagada | Reamal | Rengalbeda | SC | [6 empty] | Yes (work Started) | 55 | 55 | 65 | 10 | Estimate under preparation
| Ganjam | Buguda | A.Karadabadi | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Letter submitted to Tahasildar for identificaton of new land | To be dropped
| Ganjam | Purusottampur | B.Baragaon | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Letter submitted to Tahasildar for identificaton of new land | To be dropped
| Ganjam | Rangeilunda | Badakushasthali | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Letter submitted to Tahasildar for identificaton of new land | To be dropped
| Ganjam | Purusottampur | Baghala | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Letter submitted to Tahasildar for identificaton of new land | To be dropped
| Ganjam | Hinjilicut | Belagam | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Letter submitted to Tahasildar for identificaton of new land | To be dropped
| Ganjam | Patrapur | Buratala | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Letter submitted to Tahasildar for identificaton of new land | To be dropped
| Ganjam | Hinjilicut | Burupada | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Letter submitted to Tahasildar for identificaton of new land | To be dropped
| Ganjam | Sheragada | Gothagam | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Letter submitted to Tahasildar for identificaton of new land | To be dropped
| Ganjam | Kukudakhandi | Hugulapata | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Letter submitted to Tahasildar for identificaton of new land | To be dropped
| Ganjam | Patrapur | Jarada | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Letter submitted to Tahasildar for identificaton of new land | To be dropped
| Ganjam | Sorada | Kulangi | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Letter submitted to Tahasildar for identificaton of new land | To be dropped
| Ganjam | Sanakhemundi | Moulabhanja | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Letter submitted to Tahasildar for identificaton of new land | To be dropped
63 | Ganjam | Ganjam | Palanga | SC | 2400 | 1200 | 1200 | Yes | 0 | 0 | 0 | 55 | 55 | 65 | 10
| Ganjam | Sanakhemundi | Patiguda | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Letter submitted to Tahasildar for identificaton of new land | To be dropped
| Ganjam | Purusottampur | Raipur | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Letter submitted to Tahasildar for identificaton of new land | To be dropped
| Ganjam | Dharakote | Saba | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Letter submitted to Tahasildar for identificaton of new land | To be dropped
| Ganjam | Chikiti | Surola | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Letter submitted to Tahasildar for identificaton of new land | To be dropped
64 | Jagatsinghpur | Biridi | Arana | SC | 4000 sq ft | 1500 sq ft | yes | Yes | 0 | 0 | 0 | 55 | 55 | 65 | 10
65 | Jagatsinghpur | Kujanga | Atharabanki | SC | 0 | 0 | 0 | 0 | 2500 Sq ft | 2.5 | No | 55 | 55 | 65 | 10
| Jagatsinghpur | Raghunathpur | Babujanga | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | diverted to cuttack district | To be dropped
66 | Jagatsinghpur | Balikuda | Balikuda_Mc | SC | 0 | 0 | 0 | 0 | 3000 Sq ft | 2 km | No | 55 | 55 | 65 | 10
67 | Jagatsinghpur | Balikuda | Barmundali | SC | 0 | 0 | 0 | 0 | 3000 Sq ft | 2.1 km | No | 55 | 55 | 65 | 10
68 | Jagatsinghpur | Naugaon | Derik | SC | 0 | 0 | 0 | 0 | 2500 sq ft | 1.8 km | No | 55 | 55 | 65 | 10
69 | Jagatsinghpur | Erasama | Erasama MC | SC | 0 | 0 | 0 | 0 | 3000 sq ft | 1.8 km | No | 55 | 55 | 65 | 10
70 | Jagatsinghpur | Kujanga | Pandua | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 65 | 10 | As Hansura SC has alredy been Approved in State Plan.Now this is Diverted to Pandua.
71 | Jagatsinghpur | Tirtol | Kanakpur | SC | 0 | 0 | 0 | 0 | 2500 sq ft | 2.0 km | No | 55 | 55 | 65 | 10
72 | Jagatsinghpur | Tirtol | Kanimul | SC | 0 | 0 | 0 | 0 | 2800 sq ft | 2.5 km | No | 55 | 55 | 65 | 10
73 | Jagatsinghpur | Tirtol | Kolara | SC | 0 | 0 | 0 | 0 | 2500 sq ft | 1.8 km | No | 55 | 55 | 65 | 10
74 | Jagatsinghpur | Tirtol | Krishnandapaur | SC | 0 | 0 | 0 | 0 | 3000 sq ft | 2.2 km | No | 55 | 55 | 65 | 10
75 | Jagatsinghpur | Kujanga | Kujanga MC | SC | 0 | 0 | 0 | 0 | 2500 sq ft | 2.5 km | No | 55 | 55 | 65 | 10
76 | Jagatsinghpur | Balikuda | Borikina | SC | 0 | 0 | 0 | 0 | 3000 sq.ft. | 2.0 km | No | 55 | 55 | 65 | 10 | As Machhagaon SC has alredy been Approved in State Plan.Now this is Diverted to Borikina
77 | Jagatsinghpur | Jagatsinghpur | Mandasahi_Mc | SC | 0 | 0 | 0 | 0 | 2500 sq.ft | 2.2 km | No | 55 | 55 | 65 | 10
78 | Jagatsinghpur | Tirtol | Manijanga MC | SC | 0 | 0 | 0 | 0 | 4000 sq.ft | 2.4km | No | 55 | 55 | 65 | 10
79 | Jagatsinghpur | Jagatsinghpur | mundio | SC | 5000 Sq. ft. | 2000 sq.ft | Yes | Yes | 0 | 0 | 0 | 55 | 55 | 65 | 10
| Jagatsinghpur | Kujanga | Neherubangla | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Alredy Approved in State Plan, hence Dropped | To be dropped
| Jagatsinghpur | Erasama | Nuadhi | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Alredy Approved in State Plan, hence Dropped | To be dropped
| Jagatsinghpur | Naugaon | Nuagaon. | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Alredy Approved in State Plan, hence Dropped | To be dropped
80 | Jagatsinghpur | Kujanga | Nuagarh | SC | 0 | 0 | 0 | 0 | 2500 sq.ft. | 3 Km | 0 | 55 | 55 | 65 | 10
81 | Jagatsinghpur | Erasama | Olara | SC | 0 | 0 | 0 | 0 | 3000 sq.ft | 2.5km | No | 55 | 55 | 65 | 10
| Jharsuguda | Kirmira | Arda SC | SC | [7 empty] | 55 | 55 |  |  | New land to be indentified & existing SC is inside the campus of PHC | To be dropped
| Jharsuguda | Kirmira | Bhimjore | SC | 4350 | 800 | 3550 | No |  |  |  | 55 | 55 |  |  |  | To be dropped
| Jharsuguda | Kirmira | Chandrapur | SC | 4350 | 800 | 3550 | No |  |  |  | 55 | 55 |  |  |  | To be dropped
| Jharsuguda | Kirmira | Kadobahal | SC | 4350 | 800 | 3550 | No |  |  |  | 55 | 55 |  |  |  | To be dropped
| Jharsuguda | Kirmira | Laikera | SC | 4350 | 800 | 3550 | No |  |  |  | 55 | 55 |  |  |  | To be dropped
| Jharsuguda | Jharsuguda | Hirma | SC | 4350 | 800 | 3550 | No |  |  |  | 55 | 55 |  |  |  | To be dropped
| Jharsuguda | Jharsuguda | Marakuta | SC | 4350 | 800 | 3550 | No |  |  |  | 55 | 55 |  |  |  | To be dropped
| Jharsuguda | Lakhanpur | Pandri | SC | 4350 | 800 | 3550 | No |  |  |  | 55 | 55 |  |  |  | To be dropped
| Jharsuguda | Lakhanpur | Kirithmal | SC | 4350 | 800 | 3550 | No |  |  |  | 55 | 55 |  |  |  | To be dropped
| Jharsuguda | Lakhanpur | Tilia | SC | [7 empty] | 55 | 55 |  |  | Land to be indentified & The existing space is very small | To be dropped
82 | Jharsuguda | Lakhanpur | Sarandamal | SC | 4350 | 800 | 3550 | No |  |  |  | 55 | 55 | 65 | 10
| Kalahandi | Kesinga | Amath | SC | 6534 | 2178 | 4356 |  |  |  |  | 55 | 55 |  |  | Not Started | To be dropped
| Kalahandi | Junagarh | Atigaon | SC | 2178 | 2178 | 0 |  |  |  |  | 55 | 55 |  |  | Not Started | To be dropped
| Kalahandi | Th.Rampur | Badchatrang | SC |  |  |  |  | 4356 | 0.5 | No | 55 | 55 |  |  | Not Started | To be dropped
| Kalahandi | Jaipatna | Badtemri | SC | [7 empty] | 55 | 55 |  |  | Not Started | To be dropped
| Kalahandi | Th.Rampur | Balisara | SC | 3049 | 2178 | 871 |  |  |  |  | 55 | 55 |  |  | Not Started | To be dropped
| Kalahandi | Kalampur | Bankapala | SC | 2178 | 2178 | 0 |  |  |  |  | 55 | 55 |  |  | Not Started | To be dropped
| Kalahandi | Jaipatna | Bhairipali | SC | 2613 | 2178 | 435 |  |  |  |  | 55 | 55 |  |  | Not Started | To be dropped
| Kalahandi | Lanjigarh | Bhatangpadar | SC | 2178 | 2178 | 0 |  |  |  |  | 55 | 55 |  |  | Not Started | To be dropped
| Kalahandi | Kalampur | Bijmara | SC | 2613 | 2613 | 0 |  |  |  |  | 55 | 55 |  |  | Not Started | To be dropped
| Kalahandi | Bhawanipatna | Chahagaon | SC | 2613 | 2178 | 435 |  |  |  |  | 55 | 55 |  |  | Not Started | To be dropped
| Kalahandi | Bhawanipatna | Chheliamal | SC | 2178 | 2178 | 0 |  |  |  |  | 55 | 55 |  |  | Not Started | To be dropped
| Kalahandi | M.Rampur | Dam Karlakhunta | SC | 6534 | 2178 | 4356 |  |  |  |  | 55 | 55 |  |  | Not Started | To be dropped
| Kalahandi | Golamunda | Daspur | SC | 2178 | 2178 | 0 |  |  |  |  | 55 | 55 |  |  | Not Started | To be dropped
| Kalahandi | Bhawanipatna | Gudialipaar | SC | 2178 | 2178 | 0 |  |  |  |  | 55 | 55 |  |  | Not Started | To be dropped
| Kalahandi | Lanjigarh | Kankutru | SC | 2178 | 2178 | 0 |  |  |  |  | 55 | 55 |  |  | Not Started | To be dropped
| Kalahandi | Kesinga | Kerokuda | SC | 2178 | 2178 | 0 |  |  |  |  | 55 | 55 |  |  | Not Started | To be dropped
| Kalahandi | Kesinga | Kikia | SC | 2178 | 2178 | 0 |  |  |  |  | 55 | 55 |  |  | Not Started | To be dropped
| Kalahandi | Lanjigarh | Malipada | SC | 2178 | 2178 | 0 |  |  |  |  | 55 | 55 |  |  | Not Started | To be dropped
| Kalahandi | Lanjigarh | Musanal | SC | 3049 | 2178 | 871 |  |  |  |  | 55 | 55 |  |  | Not Started | To be dropped
| Kandhamal | Tumudibandha | Sirla | SC | 2000 | 1146 | 1000 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Not Started | To be dropped
| Kandhamal | K.Nuagaon | Baligeda | SC | 1500 | 1146 | 500 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Not Started | To be dropped
| Kandhamal | Chakapada | Baradakhole | SC | 2000 | 1146 | 1100 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Not Started | To be dropped
| Kandhamal | Phiringia | Bhrungijodi | SC | 2000 | 1146 | 1000 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Not Started | To be dropped
| Kandhamal | Daringbadi | Kundupanga | SC | 1500 | 1146 | 500 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Not Started | To be dropped
| Kandhamal | Balliguda | Kutikia | SC | 1500 | 1146 | 500 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Not Started | To be dropped
| Kandhamal | Balliguda | Landagaon | SC | 1500 | 1146 | 600 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Not Started | To be dropped
| Kandhamal | G.Udayagiri | Malikpodi | SC | 1500 | 1146 | 500 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Not Started | To be dropped
| Kandhamal | K.Nuagaon | Badeketa | SC | 1500 | 1146 | 500 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Not Started | To be dropped
| Kandhamal | Phiringia | Balandapada | SC | 1500 | 1146 | 500 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Not Started | To be dropped
| Kandhamal | Daringbadi | Bamuigaon | SC | 1500 | 1146 | 500 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Not Started | To be dropped
| Kandhamal | Chakapada | Bapilmendi-L | SC | 1500 | 1146 | 600 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Not Started | To be dropped
| Kandhamal | Balliguda | Bataguda | SC | 3000 | 1146 | 1500 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Not Started | To be dropped
| Kandhamal | Chakapada | Beheragaon | SC | 2000 | 1146 | 500 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Not Started | To be dropped
| Kandhamal | Tumudibandha | Bhandarangi | SC | 2000 | 1146 | 500 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Not Started | To be dropped
| Kandhamal | Tumudibandha | Bilamala | SC | 2000 | 1146 | 800 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Not Started | To be dropped
| Kandhamal | Tikabali | Burbinaju | SC | 2500 | 1146 | 1000 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Not Started | To be dropped
| Kandhamal | Chakapada | Chakapada | SC | 2000 | 1146 | 800 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Not Started | To be dropped
| Kandhamal | Raikia | Dadingia | SC | 2000 | 1146 | 800 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Not Started | To be dropped
| Kendrapara | Kendrapara | Balia | SC | 2500 | 1190 | 2500 |  |  |  |  | 55 | 55 |  |  | Not Initiated | To be dropped
| Kendrapara | Pattamundai | Andra | SC | 3000 | 1190 | 3000 |  |  |  |  | 55 | 55 |  |  | Not Initiated | To be dropped
| Kendrapara | Derabish | Baliabibhutipada | SC | 3500 | 1190 | 3500 |  |  |  |  | 55 | 55 |  |  | Not Initiated | To be dropped
| Kendrapara | Marshaghai | Bandhakata | SC | 2500 | 1190 | 2500 |  |  |  |  | 55 | 55 |  |  | Not Initiated | To be dropped
| Kendrapara | Mahakalapada | Barkanda | SC | 2500 | 1190 | 2500 |  |  |  |  | 55 | 55 |  |  | Not Initiated | To be dropped
| Kendrapara | Derabish | Danpur | SC | 3000 | 1190 | 3000 |  |  |  |  | 55 | 55 |  |  | Not Initiated | To be dropped
| Kendrapara | Kendrapara | Dhumat | SC | 3000 | 1190 | 3000 |  |  |  |  | 55 | 55 |  |  | Not Initiated | To be dropped
| Kendrapara | Marshaghai | Dumuka | SC | 2000 | 1190 | 2000 |  |  |  |  | 55 | 55 |  |  | Not Initiated | To be dropped
| Kendrapara | Kendrapara | Kalapada | SC | 2500 | 1190 | 2500 |  |  |  |  | 55 | 55 |  |  | Not Initiated | To be dropped
| Kendrapara | Mahakalapada | Kalatunga | SC | 2000 | 1190 | 2000 |  |  |  |  | 55 | 55 |  |  | Not Initiated | To be dropped
| Kendrapara | Marshaghai | Karilopatna | SC | 2500 | 1190 | 2500 |  |  |  |  | 55 | 55 |  |  | Not Initiated | To be dropped
| Kendrapara | Derabish | Raghudeipur | SC | 2500 | 1190 | 2500 |  |  |  |  | 55 | 55 |  |  | Not Initiated | To be dropped
| Kendrapara | Derabish | Santhapura | SC | 4000 | 1190 | 4000 |  |  |  |  | 55 | 55 |  |  | Not Initiated | To be dropped
| Kendrapara | Garadapur | Talakusuma | SC | 3000 | 1190 | 3000 |  |  |  |  | 55 | 55 |  |  | Not Initiated | To be dropped
| Kendrapara | Mahakalapada | Tarapada | SC | No | - |  |  | no |  |  | 55 | 55 |  |  | Not Initiated | To be dropped
| Kendrapara | Derabish | Tripuraripur | SC | 3000 | 1190 | 3000 |  |  |  |  | 55 | 55 |  |  | Not Initiated | To be dropped
83 | Kendujhar | Sadar | Jharbelda | SC | 4000 | 2100 | 2854 | No | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Tender stage
84 | Kendujhar | Sadar | Bodapalasa | SC | 3000 | 2100 | 1854 | No | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Tender stage
85 | Kendujhar | Harichandanpur | Badapalaspal | SC | 4000 | 2100 | 2854 | No | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Tender stage
86 | Kendujhar | Harichandanpur | Budhakhamana | SC | 4000 | 2100 | 2854 | No | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Tender stage
87 | Kendujhar | Harichandanpur | Dhagotho | SC | 4000 | 2100 | 2854 | No | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Tender stage
88 | Kendujhar | Harichandanpur | Raikala | SC | 4000 | 2100 | 2854 | No | 0 | 0 | 0 | 55 | 55 | 65 | 10 | SC diverted from Gaunighasa to Raikala
89 | Kendujhar | Ghasipura | GB Goda | SC | 4000 | 2100 | 2854 | No | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Tender stage
90 | Kendujhar | Jhumpura | Gumura | SC | 4000 | 2100 | 2854 | No | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Tender stage
91 | Kendujhar | Joda | Jalahari | SC | 4000 | 2100 | 2854 | No | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Tender stage
92 | Kendujhar | Jhumpura | Khuntapada | SC | 4000 | 2100 | 2854 | No | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Tender stage
93 | Kendujhar | Banspal | Kumundi | SC | 4000 | 2100 | 2854 | No | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Tender stage
94 | Kendujhar | Hatadihi | Orali | SC | 4000 | 2100 | 2854 | No | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Tender stage
95 | Kendujhar | Harichandanpur | Pitapiti | SC | 4000 | 2100 | 2854 | No | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Tender stage
96 | Kendujhar | Telkoi | Raisuan | SC | 4000 | 2100 | 2854 | No | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Tender stage
97 | Kendujhar | Joda | Rugudi | SC | 4000 | 2100 | 2854 | No | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Tender stage
98 | Kendujhar | Ghasipura | Saladei | SC | 4000 | 2100 | 2854 | No | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Tender stage
99 | Kendujhar | Telkoi | Sibanarayanpurguda | SC | 4000 | 2100 | 2854 | No | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Tender stage
100 | Kendujhar | Harichandanpur | Tambahara | SC | 4000 | 2100 | 2854 | No | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Tender stage
101 | Kendujhar | Champua | Parjanpur | SC | 4000 | 2100 | 2854 | No | 0 | 0 | 0 | 55 | 55 | 65 | 10 | SC diverted from Ucchabali to Parjanpur
102 | Kendujhar | Sadar | Bauripada | SC | 4000 | 2100 | 2854 | No | 0 | 0 | 0 | 55 | 55 | 65 | 10 | SC diverted from Sirisipal to Bauripada
103 | Khordha | Tangi | Achyutpur | SC | 0 | 0 | 0 | 0 | 4000 | 700.m | NO | 55 | 55 | 65 | 10 | Estimate Stage
104 | Khordha | Bolagarh | Arakhapali | SC | 0 | 0 | 0 | 0 | 4000 | 1.00Km | NO | 55 | 55 | 65 | 10 | Estimate Stage
105 | Khordha | Chilika | Badakul | SC | 3000 | 2100 | 1800 | No | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Estimate Stage
106 | Khordha | Balianta | Balakati_Mc | SC | 0 | 0 | 0 | 0 | 4000 | 1.00Km | NO | 55 | 55 | 65 | 10 | Estimate Stage
107 | Khordha | Balipatna | Balipatna_Mc | SC | 0 | 0 | 0 | 0 | 4000 | 1.00Km | NO | 55 | 55 | 65 | 10 | Estimate Stage
108 | Khordha | Chilika | Balugaon MC | SC | 0 | 0 | 0 | 0 | 4000 | 2.00Km | NO | 55 | 55 | 65 | 10 | Estimate Stage
109 | Khordha | Bolagarh | Bankoi_Mc | SC | 0 | 0 | 0 | 0 | 4000 | 2.00Km | NO | 55 | 55 | 65 | 10 | Estimate Stage
110 | Khordha | Banapur | Bhimpur | SC | 3000 | 2100 | 1800 | No | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Estimate Stage
111 | Khordha | Balianta | Bhingarpur | SC | 0 | 0 | 0 | 0 | 4000 | 2.00Km | NO | 55 | 55 | 65 | 10 | Estimate Stage
112 | Khordha | Bolagarh | Bolagarh | SC | 0 | 0 | 0 | 0 | 4000 | 2.00Km | NO | 55 | 55 | 65 | 10 | Estimate Stage
113 | Khordha | Chilika | Chasangara | SC | 0 | 0 | 0 | 0 | 4000 | 2.00Km | NO | 55 | 55 | 65 | 10 | Estimate Stage
114 | Khordha | Chilika | Haripur | SC | 0 | 0 | 0 | 0 | 4000 | 2.00Km | NO | 55 | 55 | 65 | 10 | Estimate Stage
115 | Khordha | Khordha | Kaipadar | SC | 0 | 0 | 0 | 0 | 4000 | 2.00Km | NO | 55 | 55 | 65 | 10 | Estimate Stage
116 | Khordha | Bhubaneswar | Kalyanpur | SC | 0 | 0 | 0 | 0 | 4000 | 2.00Km | NO | 55 | 55 | 65 | 10 | Estimate Stage
| Khurda | Tangi | Lalitpatpur SC | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Duplicate | To be dropped
117 | Khordha | Bhubaneswar | Mendhasal_Mc | SC | 0 | 0 | 0 | 0 | 4000 | 2.00Km | NO | 55 | 55 | 65 | 10 | Estimate Stage
118 | Khordha | Banapur | Nandapur | SC | 3000 | 2100 | 1800 | No | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Estimate Stage
119 | Khordha | Khordha | Narangarh | SC | 0 | 0 | 0 | 0 | 4000 | 500.m | NO | 55 | 55 | 65 | 10 | Estimate Stage
120 | Koraput | Semiliguda | Aligaon | sc | 3000 | 800 | 2200 |  |  |  |  | 55 | 55 | 65 | 10 | Agreement done
121 | Koraput | Borigumma | Bsingpur | sc | [7 empty] | 55 | 55 | 65 | 10
122 | Koraput | Bandhugaon | Kaberibadi | SC |  |  |  |  | NA | NA |  | 55 | 55 | 65 | 10 | Agreement done, Tahasildar has been communicated for land
123 | Koraput | Laxmipur | Laxmipur | sc |  |  |  |  | 6300 | 1.0 Km |  | 55 | 55 | 65 | 10 | Agreement to be done
124 | Koraput | Bandhugaon | Nilabadi | SC |  |  |  |  | 6500 | 0.8 Km |  | 55 | 55 | 65 | 10 | Agreement done
125 | Malkanagiri | Malkangiri | B.L Pur | SC | - | - | - | - | 3500 Sqft. | 1 km | No | 55 | 55 | 65 | 10 | permission to be taken up the work has not yet been received from the MD, NHM
126 | Malkanagiri | Mathili | Bhejaguda | SC | - | - | - | - | 3700 Sqft. | 300M | No | 55 | 55 | 65 | 10
127 | Malkanagiri | Korukonda | Challanguda | SC | - | - | - | - | 3500 Sqft. | 350M | No | 55 | 55 | 65 | 10
128 | Malkanagiri | Mathili | Chaulmendi | SC | - | - | - | - | 3100 Sqft. | 500M | No | 55 | 55 | 65 | 10
129 | Malkanagiri | Mathili | Dalpatiguda | SC | - | - | - | - | 3300 Sqft. | 270M | No | 55 | 55 | 65 | 10
130 | Malkanagiri | Mathili | Dhungiaput | SC | - | - | - | - | 3800 Sqft. | 370M | No | 55 | 55 | 65 | 10
131 | Malkanagiri | Malkangiri | Goudaguda | SC | - | - | - | - | 2900 Sqft. | 280M | No | 55 | 55 | 65 | 10
132 | Malkanagiri | Khairput | Kadamguda | SC | - | - | - | - | 3200 Sqft. | 310M | No | 55 | 55 | 65 | 10
133 | Malkanagiri | Mathili | Kaliaguda | SC | - | - | - | - | 3400 Sqft. | 900M | No | 55 | 55 | 65 | 10
134 | Malkanagiri | Mathili | Korapalli | SC | - | - | - | - | 3000 Sqft. | 500M | No | 55 | 55 | 65 | 10
135 | Malkanagiri | Khairput | Kunmarput | SC | - | - | - | - | 3100 Sqft. | 1Km | No | 55 | 55 | 65 | 10
136 | Malkanagiri | Korukonda | M.V.-109 | SC | - | - | - | - | 3300 Sqft. | 800M | No | 55 | 55 | 65 | 10
137 | Malkanagiri | Malkangiri | M.V-92 | SC | - | - | - | - | 3200 Sqft. | 500M | No | 55 | 55 | 65 | 10
138 | Malkanagiri | Kalimela | Manyamkonda | SC | - | - | - | - | 3500 Sqft. | 300M | No | 55 | 55 | 65 | 10
139 | Malkanagiri | Podia | Materu | SC | - | - | - | - | 3600 Sqft. | 200M | No | 55 | 55 | 65 | 10
140 | Malkanagiri | Podia | Motu | SC | - | - | - | - | 3300 Sqft. | 400M | No | 55 | 55 | 65 | 10
141 | Malkanagiri | Khairput | Muduliguda | SC | - | - | - | - | 3800 Sqft. | 400M | No | 55 | 55 | 65 | 10
142 | Malkanagiri | K.Gumma | Muduliguda | SC | - | - | - | - | 3800 Sqft. | 400M | No | 55 | 55 | 65 | 10
143 | Malkanagiri | K.Gumma | Naliguda | SC | - | - | - | - | 3200 Sqft. | 1Km | No | 55 | 55 | 65 | 10
144 | Mayurbhanj | Khunta | Badapather | SC | 3400 Sqft | 1100 Sqft | 2300 Sqft | 0 | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Estimate stage
145 | Mayurbhanj | Khunta | Bahanada | SC | 3200 Sqft | 1100 Sqft | 2100 Sqft | 0 | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Estimate stage
146 | Mayurbhanj | Khunta | Dhanapana | SC | 3000 Sqft | 800 Sqft | 2200 Sqft | 0 | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Estimate stage
147 | Mayurbhanj | Khunta | Dhanghera | SC | 3500 Sqft | 1100 Sqft | 2400 Sqft | 0 | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Estimate stage
148 | Mayurbhanj | Kaptipada | Katuria | SC | 0 | 0 | 0 | 0 | 4356 Sqft | 1km to 2km | No | 55 | 55 | 65 | 10 | Appplied for land requition
149 | Mayurbhanj | Khunta | Mahuldihi | SC | 0 | 0 | 0 | 0 | 3200 Sqft | Existing Building not avilable | No | 55 | 55 | 65 | 10 | New Land Applied to Tahasildar
150 | Mayurbhanj | Khunta | Tikerpada | SC | 0 | 0 | 0 | 0 | 3500 Sft | 2 km | No | 55 | 55 | 65 | 10 | New Land Applied to Tahasildar
151 | Mayurbhanj | G.B Nager | Vandagaon | SC | 2500 Sqft | 1100 Sqft | 1400Sft | Yes | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Estimate stage
152 | Nabarangpur | tentulikhunti | Amlabhata | Sc | 0 | 0 | 0 | 0 | 8000 | 2km | no | 55 | 55 | 65 | 10
153 | Nabarangpur | Chandahandi | Anabeda | SC | 0 | 0 | 0 | 0 | 8000 | 1.5 km | no | 55 | 55 | 65 | 10
154 | Nabarangpur | Tentulikhunti | Anchalaguma | SC | 0 | 0 | 0 | 0 | 8000 | 3km | no | 55 | 55 | 65 | 10
155 | Nabarangpur | Kosagumuda | Asanga | SC | 0 | 0 | 0 | 0 | 8500 | 3km | no | 55 | 55 | 65 | 10
156 | Nabarangpur | Kosagumuda | Bada-amada | SC | 0 | 0 | 0 | 0 | 8500 | 3km | no | 55 | 55 | 65 | 10
157 | Nabarangpur | Umerkote | Bada-bharandi | SC | 0 | 0 | 0 | 0 | 8500 | 3km | no | 55 | 55 | 65 | 10
158 | Nabarangpur | Umerkote | Bakada | SC | 4500 | 1000 | 2500 | 0 | 0 | 0 | 0 | 55 | 55 | 65 | 10
159 | Nabarangpur | Sanomosigam | Basini | Sc | 0 | 0 | 0 | 0 | 8500 | 3km | no | 55 | 55 | 65 | 10
160 | Nabarangpur | Chandahandi | Beheramunda | SC | 0 | 0 | 0 | 0 | 8500 | 3km | no | 55 | 55 | 65 | 10
161 | Nabarangpur | Jharigam | Belgam | SC | 0 | 0 | 0 | 0 | 8500 | 3km | no | 55 | 55 | 65 | 10
162 | Nabarangpur | Tentulikhunti | Pujariguda | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 65 | 10 | SC diverted from Biriguda SC of Papadahandi block to pujariguda sc of tentulikhunti block
163 | Nabarangpur | Umerkote | Chachanbeda | SC | 5000 | 1500 | 3000 | 0 | 0 | 0 | 0 | 55 | 55 | 65 | 10
164 | Nabarangpur | Chandahandi | Chandahandi | SC | 0 | 0 | 0 | 0 | 8500 | 3km | no | 55 | 55 | 65 | 10
165 | Nabarangpur | Sanomosigam | Chatahandi | Sc | 0 | 0 | 0 | 0 | 8500 | 3km | no | 55 | 55 | 65 | 10
166 | Nabarangpur | Dabugam | Dabugam | SC | 0 | 0 | 0 | 0 | 8500 | 3km | no | 55 | 55 | 65 | 10
167 | Nabarangpur | Chandahandi | Dalabeda | SC | 0 | 0 | 0 | 0 | 8500 | 3km | no | 55 | 55 | 65 | 10
168 | Nabarangpur | Nandahandi | Dangarbheja | SC | 0 | 0 | 0 | 0 | 8500 | 3km | no | 55 | 55 | 65 | 10
169 | Nabarangpur | Jharigam | Deulakana | SC | 0 | 0 | 0 | 0 | 8500 | 3km | no | 55 | 55 | 65 | 10
170 | Nabarangpur | Jharigam | Dhodra | SC | 0 | 0 | 0 | 0 | 8500 | 3km | no | 55 | 55 | 65 | 10
171 | Nayagada | Odagaon | Badagorada | SC | 2000 | 1250 | 750 | No | 4000 | 1 kilometer | Yes | 55 | 55 | 60.5 | 5.5
| Nayagarh | Gania | Badasilinga | SC | 4000 | Na | - | - | - | - | - | 55 | 55 |  |  | The same completed in IPHS norn & handed over to end user | To be dropped
172 | Nayagada | Nuagaon | Balanda | SC | 2550 | 1250 | 1300 | No | 4000 | 1 kilometer | Yes | 55 | 55 | 60.5 | 5.5
173 | Nayagada | Nayagada | Baunsiapada | SC | 2000 | 1250 | 750 | No | 4000 | 1 kilometer | Yes | 55 | 55 | 60.5 | 5.5
174 | Nayagada | Nuagaon | Beruanbari | SC | 3600 | 2500 | 1100 | No | 4000 | 1 kilometer | Yes | 55 | 55 | 60.5 | 5.5
175 | Nayagada | Ranpur | Brajarajpur | SC | 3000 | 1250 | 1750 | No | 4000 | 1 kilometer | Yes | 55 | 55 | 60.5 | 5.5
176 | Nayagada | Gania | Gania MC | SC |  |  |  |  | 4000 | 1 kilometer | Yes | 55 | 55 | 60.5 | 5.5
177 | Nayagada | Daspalla | Ghugudipada | SC | 3000 | 2100 | 900 | No | 4000 | 1 kilometer | Yes | 55 | 55 | 60.5 | 5.5
178 | Nayagada | Daspalla | Golahandi | SC | 1300 | 1250 | 50 | No | 4000 | 1 kilometer | Yes | 55 | 55 | 60.5 | 5.5
179 | Nayagada | Odagaon | Goudaput | SC | 1500 | 1250 | 250 | No | 4000 | 1 kilometer | Yes | 55 | 55 | 60.5 | 5.5
180 | Nayagada | Khandapada | J. Prasad | SC | 2000 | 1250 | 750 | No | 4000 | 1 kilometer | Yes | 55 | 55 | 60.5 | 5.5
181 | Nayagada | Bhapur | Kainfulia | SC | 2000 | 1250 | 750 | No | 4000 | 1 kilometer | Yes | 55 | 55 | 60.5 | 5.5
182 | Nayagada | Odagaon | Kesapania | SC | 2500 | 1250 | 1250 | No | 4000 | 1 kilometer | Yes | 55 | 55 | 60.5 | 5.5
183 | Nayagada | Khandapada | Koska | SC | 4000 | 1250 | 2750 | No | 4000 | 1 kilometer | Yes | 55 | 55 | 60.5 | 5.5
184 | Nayagada | Khandapada | Laxmiprasad | SC | 4000 | 1250 | 2750 | No | 4000 | 1 kilometer | Yes | 55 | 55 | 60.5 | 5.5
185 | Nayagada | Ranpur | Majhiakhanda | SC | 2500 | 1250 | 1250 | No | 4000 | 1 kilometer | Yes | 55 | 55 | 60.5 | 5.5
186 | Nayagada | Bhapur | Marada | SC | 2500 | 1250 | 1250 | No | 4000 | 1 kilometer | Yes | 55 | 55 | 60.5 | 5.5
| Nuapada | Khariar | Badamaheswr | SC |  |  |  |  | No |  |  | 55 | 55 |  |  | Not Yet Started | To be dropped
| Nuapada | Nuapada | Beltukuri | SC | 1200 sqft | 900 sqft | 300 sqft | No |  |  |  | 55 | 55 |  |  | Not Yet Started | To be dropped
| Nuapada | Komna | Bhela | SC | 1200 sqft | 900 sqft | 300 sqft | No |  |  |  | 55 | 55 |  |  | Not Yet Started | To be dropped
| Nuapada | Sinapali | Kendumunda | SC | 1200 sqft | 900 sqft | 300 sqft | No |  |  |  | 55 | 55 |  |  | Not Yet Started | To be dropped
| Nuapada | Khariar | Kirkita | SC | 1200 sqft | 900 sqft | 300 sqft | No |  |  |  | 55 | 55 |  |  | Not Yet Started | To be dropped
| Nuapada | Khariar | Lanji | SC | 1200 sqft | 900 sqft | 300 sqft | No |  |  |  | 55 | 55 |  |  | Not Yet Started | To be dropped
| Nuapada | Sinapali | Makhapadar | SC | 1200 sqft | 900 sqft | 300 sqft | No |  |  |  | 55 | 55 |  |  | Not Yet Started | To be dropped
187 | Puri | Pipili | Binayakpur | SC | 2210 | 1149 | 486 | 231 | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Estimated under Preparation
| Puri | Kakatpur | Amuniapatana | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Land not Available. Selection in process | To be dropped
188 | Puri | Astaranga | Astaranga | SC | 1200 | 1149 | 300 | 0 | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Estimated under Preparation
| Puri | GOP | Balibasta | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Land not Available. Selection in process | To be dropped
189 | Puri | Kakatpur | Balidokan | SC | 2000 | 1149 | 600 | 0 | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Estimated under Preparation
| Puri | Puri Sadar | Baliput | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Land not Available. Selection in process | To be dropped
190 | Puri | GOP | Bedapur | SC | 2500 | 1149 | 1000 | 0 | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Estimated under Preparation
191 | Puri | GOP | Birtunga | SC | 1500 | 1149 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Estimated under Preparation
192 | Puri | Nimapara | Brahamakundi | SC | 2500 | 1149 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Estimated under Preparation
193 | Puri | Puri Sadar | Chalisibatia | SC | 4500 | 1149 | 1900 | 0 | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Estimated under Preparation
| Puri | Puri Sadar | Chandanpur | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Land not Available. Selection in process | To be dropped
| Puri | GOP | Chhaitana | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Land not Available. Selection in process | To be dropped
194 | Puri | Krushnaprasad | Chilikanuapada | SC | 60168 | 1149 | 59019 | 0 | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Estimated under Preparation
| Puri | Delanga | Delanga | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Land not Available. Selection in process | To be dropped
195 | Puri | sata]yabadi | Gabakunda | SC | 11000 | 1149 | 5500 | 0 | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Estimated under Preparation
| Puri | GOP | Inchara | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Land not Available. Selection in process | To be dropped
| Puri | Delanga | Kalyanpur | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Land not Available. Selection in process | To be dropped
| Puri | Kanas | Kanas | SC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 |  |  | Land not Available. Selection in process | To be dropped
196 | Puri | GOP | Konark | SC | 2500 | 1149 | 1200 | 400 | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Estimated under Preparation
197 | Puri | Kakatpur | Kurujanga | SC | 2400 | 1149 | 1200 | 0 | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Estimated under Preparation
198 | Puri | sata]yabadi | Mahura | SC | 12000 | 1149 | 200 | 0 | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Estimated under Preparation
199 | Rayagada | Ramanaguda | Parikhiti | sc | No | No | No | No | 6000 | 30 mtr | No | 55 | 55 | 65 | 10 | Requested for allocation of additional budget
200 | Rayagada | Kasipur | Adajar | SC | No | No | No | No | 6000 | 50 mtr | No | 55 | 55 | 65 | 10 | Requested for allocation of additional budget
201 | Rayagada | K. Singpur | Aljiniguda | SC | 6000 | 1146 | 3000 | No | 0 | 0 | 0 | 55 | 55 | 65 | 10 | Requested for allocation of additional budget
202 | Rayagada | Rayagada | Amalabhata | SC | No | 0 | 0 | No | 5000 | 100 mtr | No | 55 | 55 | 65 | 10 | Requested for allocation of additional budget
203 | Rayagada | K. Singpur | Bada Bamuniguda | SC | No | 0 | 0 | No | 5000 | 50 mtr | No | 55 | 55 | 65 | 10 | Requested for allocation of additional budget
204 | Rayagada | K. Singpur | Badaduar | SC | No | 0 | 0 | No | 5000 | 50mtr | No | 55 | 55 | 65 | 10 | Requested for allocation of additional budget
205 | Rayagada | Muniguda | Badamudra | SC | No | 0 | 0 | No | 5000 | 200mtr | No | 55 | 55 | 65 | 10 | Requested for allocation of additional budget
206 | Rayagada | Kasipur | Badijharana | SC | No | 0 | 0 | No | 5000 | 100 mtr | No | 55 | 55 | 65 | 10 | Requested for allocation of additional budget
207 | Rayagada | Gunupur | Baghasoal | SC | No | 0 | 0 | No | 5000 | 1km | No | 55 | 55 | 65 | 10 | Requested for allocation of additional budget
208 | Rayagada | Padmapur | Bahupadar | SC | No | 0 | 0 | No | 5000 | 200 mtr | No | 55 | 55 | 65 | 10 | Requested for allocation of additional budget
209 | Rayagada | Kasipur | Bankamba | SC | No | 0 | 0 | No | 5000 | 600 mtr | No | 55 | 55 | 65 | 10 | Requested for allocation of additional budget
210 | Rayagada | Kolnara | Bankili | SC | No | 0 | 0 | No | 5000 | 1km | No | 55 | 55 | 65 | 10 | Requested for allocation of additional budget
211 | Rayagada | Kasipur | Bartibali | SC | No | 0 | 0 | No | 5000 | 20mtr | No | 55 | 55 | 65 | 10 | Requested for allocation of additional budget
212 | Rayagada | Chandrapur | Belamguda | SC | No | 0 | 0 | No | 5000 | 100mtr | No | 55 | 55 | 65 | 10 | Requested for allocation of additional budget
213 | Rayagada | Bisamakatak | Bethiapada | SC | No | 0 | 0 | No | 5000 | 10mtr | No | 55 | 55 | 65 | 10 | Requested for allocation of additional budget
214 | Rayagada | Ramanaguda | Bhamini | SC | No | 0 | 0 | No | 5000 | 20mtr | No | 55 | 55 | 65 | 10 | Requested for allocation of additional budget
215 | Rayagada | Bisamakatak | Bhatapur | SC | No | 0 | 0 | No | 5000 | 20mtr | No | 55 | 55 | 65 | 10 | Requested for allocation of additional budget
216 | Rayagada | Gunupur | Bhimapur | SC | No | 0 | 0 | No | 5000 | 0 | No | 55 | 55 | 65 | 10 | Requested for allocation of additional budget
217 | Rayagada | Chandrapur | Bijapur | SC | No | 0 | 0 | No | 5000 | 30mtr | No | 55 | 55 | 65 | 10 | Requested for allocation of additional budget
218 | Sambalpur | Dhankauda | A.Katapali | SC | [7 empty] | 55 | 55 | 65 | 10
219 | Sambalpur | Jujumura | Badasahir | SC | [7 empty] | 55 | 55 | 65 | 10
220 | Sambalpur | Dhankauda | Berhampura | SC | [7 empty] | 55 | 55 | 65 | 10
221 | Sambalpur | Jamankira | Bhojpur | SC | [7 empty] | 55 | 55 | 65 | 10
222 | Sambalpur | Jujumura | Birsinghgarh | SC | [7 empty] | 55 | 55 | 65 | 10
223 | Sambalpur | Dhankauda | Bisalkhinda - II | SC | 4300 Sft | 800 sft | 3500 sft |  | 4350 |  |  | 55 | 55 | 65 | 10 | Permission received from State office for execution
224 | Sambalpur | Kuchinda | Boxama | SC | [7 empty] | 55 | 55 | 65 | 10
225 | Sambalpur | Dhankauda | Chaurnpur | SC | [7 empty] | 55 | 55 | 65 | 10
226 | Sambalpur | Jujumura | Dangarpada | SC | 4300 Sft | 800 sft | 3500 sft |  | 4350 |  |  | 55 | 55 | 65 | 10 | Permission received from State office for execution
227 | Sambalpur | Dhankauda | Dengimocha | SC | [7 empty] | 55 | 55 | 65 | 10
228 | Sambalpur | Maneswar | Dhama | SC | [7 empty] | 55 | 55 | 65 | 10
229 | Sambalpur | Naktideul | Doincha | SC | [7 empty] | 55 | 55 | 65 | 10
230 | Sambalpur | Kuchinda | Gochhara | SC | [7 empty] | 55 | 55 | 65 | 10
231 | Sambalpur | Jujumura | Jujumura | SC | 4300 Sft | 800 sft | 3500 sft |  | 4350 |  |  | 55 | 55 | 65 | 10 | Permission received from State office for execution
232 | Sambalpur | Dhankauda | Kainsir | SC | [7 empty] | 55 | 55 | 65 | 10
233 | Sambalpur | Jamankira | Kenadhipa | SC | [7 empty] | 55 | 55 | 65 | 10
234 | Sambalpur | Rengali | Khuntlamal | SC | 4300 Sft | 800 sft | 3500 sft |  | 4350 |  |  | 55 | 55 | 65 | 10 | Permission received from State office for execution
235 | Sambalpur | Dhankauda | Kilasama | SC | [7 empty] | 55 | 55 | 65 | 10
236 | Sambalpur | Naktideul | Kisinda | SC |  |  |  |  | 4350 | 1KM |  | 55 | 55 | 65 | 10 | Permission received from State office for execution
237 | Sambalpur | Dhankauda | Kudgunderpur | SC | [7 empty] | 55 | 55 | 65 | 10
238 | Sambalpur | Jujumura | Kukudapali | SC | [7 empty] | 55 | 55 | 65 | 10
239 | Sambalpur | Kuchinda | Kuturachuan | SC | [7 empty] | 55 | 55 | 65 | 10
240 | Sambalpur | Kuchinda | Laidaguna | SC | 4300 Sft | 800 sft | 3500 sft |  | 4350 |  |  | 55 | 55 | 65 | 10 | Permission received from State office for execution
241 | Sambalpur | Jujumura | Lipinda | SC |  |  |  |  | 4350 | 0.5 KM |  | 55 | 55 | 65 | 10 | Permission received from State office for execution
242 | Sambalpur | Jamankira | Mahada | SC | 4300 Sft | 800 sft | 3500 sft |  | 4350 |  |  | 55 | 55 | 65 | 10 | Permission received from State office for execution
243 | Sonpur | Sonpur | Babupali | SC |  |  |  |  | 4350 | 500 mtr | Allination in process | 55 | 55 | 65 | 10 | khata no-198 plot no-652 , 0.10 dec
244 | Sonpur | Sonpur | Badynath | SC |  |  |  |  | 4350 | 500 mtr |  | 55 | 55 | 65 | 10 | khata no-365 plot no-699,700,703 , 0.10 dec
245 | Sonpur | B.M.Pur | Bahalpadar | SC |  |  |  |  | 4350 | 5 mtr |  | 55 | 55 | 65 | 10 | khata no-152 plot no-1357 , 0.10 dec
246 | Sonpur | Binika | Bankighiridi | SC |  |  |  |  | 4350 | 500 mtr |  | 55 | 55 | 65 | 10 | khata no-453 ,plot no-1668 , 0.16 dec
247 | Sonpur | Dunguripali | Beheramal | SC |  |  |  | YES |  |  |  | 55 | 55 | 65 | 10 | in Existing old building
248 | Sonpur | Ullunda | Bidurupali | SC |  |  |  | YES |  |  |  | 55 | 55 | 65 | 10 | in Existing old building
249 | Sonpur | Dunguripali | Dunguripali MC | SC |  |  |  | YES |  |  |  | 55 | 55 | 65 | 10 | in Existing old building
250 | Sonpur | B.M.Pur | Jatesingha | SC |  |  |  |  | 4350 | 3 mtr | Allination in process | 55 | 55 | 65 | 10 | khata no-339 ,plot no-1259 , 0.10 dec
251 | Sonpur | Ullunda | Jaunbhaunra | SC |  |  |  |  | 4350 | 6mtr |  | 55 | 55 | 65 | 10 | khata no-112,plot no-253, 0.10 dec
252 | Sonpur | Ullunda | KALAPATHAR | SC |  |  |  | YES |  |  |  | 55 | 55 | 65 | 10 | in Existing old building
253 | Sonpur | Binika | Mahulpali | SC |  |  |  |  | 4350 | 600mtr | Allination in process | 55 | 55 | 65 | 10 | khata no-148 ,plot no-32 , 0.10 dec
254 | Sonpur | B.M.Pur | Masinapali | SC |  |  |  |  | 4350 | 4mtr |  | 55 | 55 | 65 | 10 | khata no-62 ,plot no-265 , 0.10 dec
255 | Sonpur | Tarva | Naktikana | SC |  |  |  | YES |  |  |  | 55 | 55 | 65 | 10 | in Existing old building
256 | Sonpur | Ullunda | Panchmahala | SC |  |  |  | YES |  |  |  | 55 | 55 | 65 | 10 | in Existing old building
257 | Sonpur | Sonpur | Rengali | SC |  |  |  |  | 4350 | 500 mtr |  | 55 | 55 | 65 | 10 | khata no-237 ,plot no-672 , 0.10 dec
258 | Sonpur | Ullunda | Sindhol | SC |  |  |  |  | 4350 | 500mtr |  | 55 | 55 | 65 | 10 | khata no-248 ,plot no-440 , 0.10 dec
259 | Sonpur | Binika | Sindurpur | SC |  |  |  | YES |  |  |  | 55 | 55 | 65 | 10 | in Existing old building
260 | Sonpur | Dunguripali | Tamamura | SC | [6 empty] | shetch map to be submitted | 55 | 55 | 65 | 10 | Letter issued to tahasidar letter no-1676 on dt 09.07.2025
261 | Sundaragada | Nuagaon | Badjojoda | SC |  |  |  |  | 4356 | 1 KM | Yes | 55 | 55 | 65 | 10 | Awaiting for approval, from MD NHM
262 | Sundaragada | Balisankara | Balisankara | SC |  |  |  |  | 4300 | 2.5 KM | Yes | 55 | 55 | 65 | 10 | Awaiting for approval, from MD NHM
263 | Sundaragada | Bonaigarh | Bandhabhuin | SC |  |  |  |  | 5227 | 1.8 KM | Yes | 55 | 55 | 65 | 10 | Awaiting for approval, from MD NHM
264 | Sundaragada | Gurundia | Banki | SC |  |  |  |  | 4356 | 0.5 KM | Yes | 55 | 55 | 65 | 10 | Estimate under preparation
265 | Sundaragada | Lathikata | Beldihi | SC | 4792 | 1650 | 2700 |  |  |  |  | 55 | 55 | 65 | 10 | Estimate under preparation
266 | Sundaragada | Gurundia | Bijadihi | SC | 10454 | 800 | 9574 |  |  |  |  | 55 | 55 | 65 | 10 | Estimate under preparation
267 | Sundaragada | Balisankara | Bondega | SC |  |  |  |  | 4300 | 1.6 KM | Yes | 55 | 55 | 65 | 10 | Awaiting for approval, from MD NHM
268 | Sundaragada | Gurundia | Boneikela | SC |  |  |  |  | 8712 | 1 KM | Yes | 55 | 55 | 65 | 10 | Awaiting for approval, from MD NHM
269 | Sundaragada | Koira | Chordhara | SC | [7 empty] | 55 | 55 | 65 | 10 | Awaiting for approval, from MD NHM, Land Identified & demarcation is Process
270 | Sundaragada | Lephripara | Darlipali | SC | 4356 | 2000 | 2000 | Yes |  |  |  | 55 | 55 | 65 | 10 | Estimate under preparation
271 | Sundaragada | Hemgir | Duduka | SC |  |  |  |  | 4356 | 2.5 KM | Yes | 55 | 55 | 65 | 10 | Estimate under preparation
272 | Sundaragada | Lephripara | Dumabahal | SC |  |  |  |  | 4356 | 1.5 KM | Yes | 55 | 55 | 65 | 10 | Estimate under preparation
273 | Sundaragada | Lahunipara | Fuljhar | SC | [7 empty] | 55 | 55 | 65 | 10 | Awaiting for approval, from MD NHM, Land Identified & demarcation is Process
274 | Sundaragada | Kutra | Gairbahal | SC | 4356 | 600 | 3500 | Yes |  |  |  | 55 | 55 | 65 | 10 | Estimate under preparation
275 | Sundaragada | Bonaigarh | Ghosra | SC |  |  |  |  | 4356 | 1.5 KM | Yes | 55 | 55 | 65 | 10 | Awaiting for approval, from MD NHM
276 | Sundaragada | Lephripara | Gundiadihi | SC |  |  |  |  | 4356 | 2.0 KM | Yes | 55 | 55 | 65 | 10 | Estimate under preparation
277 | Sundaragada | Hemgir | Hemgir | SC |  |  |  |  | 4356 | 2.0 KM | Yes | 55 | 55 | 65 | 10 | Estimate under preparation
278 | Sundaragada | Gurundia | Jarada | SC | [7 empty] | 55 | 55 | 65 | 10 | Awaiting for approval, from MD NHM, Land Identified & demarcation is Process
279 | Sundaragada | Gurundia | Jhaliadihi | SC |  |  |  |  | 10018 | 1.5 KM | Yes | 55 | 55 | 65 | 10 | Awaiting for approval, from MD NHM
| Total | [10 empty] | 22495 | 22495 | 17921.38 | 2576.38